## FFY 2020-21 9.28
MTC FFY 2020-21 Annual Obligation Plan | [43 empty] | Remarks | Field Review (mm/dd/yy) | RFA Submission (EDS or Actual) (mm/dd/yy) | TIP Prog Year | Conf in Plan
Project List | [20 empty] | Remaining | 101738011 | 73083708 | 174821719 |  | Obligations |  |  |  |  | Total |  | 101738011 | 73083708 | 174821719 |  | Fund Type |  |  |  |  | Total | Remaining | [7 empty] | Total
2020-09-30 | [12 empty] | CTC Allocation |  | Obligation | [5 empty] | Balance | STP | CMAQ | STP/CMAQ | HSIP | HBP | RTIP | ATP | SB1 | Earmark | Obligations |  | STP | CMAQ | STP/CMAQ | HSIP | HBP | RTIP | ATP | SB1 | EARMARK | Programmed | Balance | Enter comments or additional information. Provide contact names & phone numbers or email addresses for questions. | [6 empty] | Programmed
County | Local Agency | TIP ID | FMS ID | Unique ID | Program | Fund Source | FPN | FPN | FPN | FPN | Phase | Project Title | Latest Action | CTC Allocation | Latest Action | Latest Action | Planned | Planned or | Planned | Oblig/Alloc | 98.52% | 0% | 0% | 0% | 0% | 1.27% | 0% | 0% | 0% | 0% | 0.4312% | Oblig | 23.4% | 8.026% | 31.43% | 4.198% | 15.25% | 33.96% | 15.11% | 0% | 0.05737% | 100% | 99.57% | [5 empty] | Dated Added | Entered in | 100%
[13 empty] | Status | Date | Status | Date | Award | Field Review | Oblig | Deadline | 280786620.4821 | 0 | 0 | 0 | 0 | 1229020 | 0 | 0 | 0 | 0 | 1229020 | Date | 66690353 | 22876360 | 89566713 | 11965163 | 43476251.4821 | 96779000 | 43065000 | 0 | 163513 | 285015640.4821 | 283786620.4821 | [5 empty] | to Plan | FMS | 285015640.4821
County | Sponsor | TIP ID | FMS ID | Unique ID | Program | Fund Source | Prefix | LoCode | Proj # | FPN | Phase | Project Title | Latest Action | CTC Allocation | Latest Action | Action Date | Planned Award | Field Review | Planned Oblig | Deadline | Balance | STP | CMAQ | STP/CMAQ | HSIP | Seismic | RTIP | ATP | SB1 | EARMARK | Oblig Amount | Oblig Date | STP | CMAQ | STP/CMAQ | HSIP | Seismic | STIP | ATP | SB1 | EARMARK | Total | Balance | Remarks | Field Review | RFA | Prog Year | Resp'd? | Dated Added | DATE | Total
Alameda | Alameda | ALA170049 | 6539 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED |  | 5014 |  | -5014() | PSE | Central Avenue Safety Improvements |  |  |  |  | 2022-09-01 | 4/2020 (PID) |  | 2021-06-30 | 300000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 300000 |  |  | 300000 | 300000 | 8/28 - Project will be moved out to FFY 21/22. Waiting for CTC Action |  |  |  |  | 2020-09-30 |  | 300000
Alameda | Alameda | ALA170049 | 6539 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED |  | 5014 |  | -5014() | CON | Central Avenue Safety Improvements |  |  |  |  | 2022-09-01 | 4/2020 (PID) |  | 2021-06-30 | 6846000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 6846000 |  |  | 6846000 | 6846000 | 8/28 - Project will be moved out to FFY 21/22. Waiting for CTC Action. |  |  |  |  | 2020-09-30 |  | 6846000
Alameda | Alameda | ALA170074 | 6760 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5014 |  | -5014() | CON | Alameda City-Wide Pavemnet Rehabilitation |  |  |  |  | 2020-10-01 | 2021-05-01 |  | 2021-01-31 | 827000 |  |  | 0 | [6 empty] | 0 |  | 827000 |  | 827000 | [6 empty] | 827000 | 827000 | [5 empty] | 2020-09-30 |  | 827000
Alameda | Alameda County | ALA130018 | 5794 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5933 | 160 | STPL-5933(160) | CON | Alameda Co-Various Streets and Roads Preservation | [7 empty] | 2021-06-30 | 2171000 |  |  | 0 | [6 empty] | 0 |  | 2171000 |  | 2171000 | [6 empty] | 2171000 | 2171000 | [5 empty] | 2020-09-30 |  | 2171000
Alameda | Albany | ALA170088 | 6743 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5178 |  | -5178() | CON | San Pablo Ave & Buchanan St Pedestrian Imps. |  |  |  |  | 2021-05-01 | 2020-10-01 |  | 2021-06-30 | 340000 |  |  | 0 | [6 empty] | 0 |  | 340000 |  | 340000 | [6 empty] | 340000 | 340000 | 8/28 - Project will be moved out to FFY 21/22. Plan to obligate June 2021 |  |  |  |  | 2020-09-30 |  | 340000
Alameda | ACTC | ALA050079 | 163 | RIP-T5-18-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | CON | I-80 Gilman Interchange Improvements | [5 empty] | 6/2018 (NEPA) |  | 2020-11-13 | 8979000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 8979000 |  |  |  | 8979000 | 8979000 | [5 empty] | 2020-09-30 |  | 8979000
Alameda | ACTC | ALA050079 | 163 | RIP-T5-18-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | CON | I-80 Gilman Interchange Improvements | [5 empty] | 6/2018 (NEPA) |  | 2020-11-13 | 14360000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 14360000 |  |  |  | 14360000 | 14360000 | [5 empty] | 2020-09-30 |  | 14360000
Alameda | ACTC | ALA050079 | 163 | RIP-T5-20-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | CON | I-80 Gilman Interchange Improvements | [5 empty] | 6/2018 (NEPA) |  | 2020-11-13 | 15445000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 15445000 |  |  |  | 15445000 | 15445000 | [5 empty] | 2020-09-30 |  | 15445000
Alameda | AC Transit |  | 7129 | RIP-T5-20-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | CON | AC Transit Purchase buses for Transbay service | [7 empty] | 2021-06-30 | 13125000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 13125000 |  |  |  | 13125000 | 13125000 | [5 empty] | 2020-09-30 |  | 13125000
Alameda | Hayward | ALA170066 | 6737 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5050 |  | -5050() | CON | Winton Ave Complete Street |  |  |  |  | 2020-11-01 | 2019-03-01 |  | 2021-01-31 | 1662000 |  |  | 0 | [6 empty] | 0 |  | 1662000 |  | 1662000 | [6 empty] | 1662000 | 1662000 | 8/28 - Confirmed for FFY20/21 |  |  |  |  | 2020-09-30 |  | 1662000
Alameda | Oakland | ALA170043 | 6531 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5012 | 154 | ATPL-5012(154) | PSE | 14th Street: Safe Routes in the City |  |  |  |  | 2020-02-28 | 2018-06-01 |  | 2020-12-31 | 1235000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 1235000 |  |  | 1235000 | 1235000 | 8/28 - Project pushed out to FFY 21/22. Waiting for CTC extension approval |  |  |  |  | 2019-10-01 |  | 1235000
Alameda | Oakland | ALA170043 | 6531 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5012 |  | ATPL-5012() | CON | 14th Street: Safe Routes in the City |  |  |  |  | 2022-05-20 | 2018-06-01 |  | 2020-12-31 | 9343000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 9343000 |  |  | 9343000 | 9343000 | 8/28 - Project pushed out to FFY 21/22. Waiting for CTC extension approval 3/23 - Ext CON request to 2022 at May CTC meeting. 8/19 - Sponsor will apply for ext by 11/1/19 |  |  |  |  | 2019-10-01 |  | 9343000
Alameda | Piedmont | ALA170084 | 6757 | STP-T5-OBAG2-CO | OBAG 2 | STP |  |  |  | -() | CON | Piedmont - Oakland Avenue Improvements | [7 empty] | 2021-06-30 | 168000 |  |  | 0 | [6 empty] | 0 |  | 168000 |  | 168000 | [6 empty] | 168000 | 168000 | [5 empty] | 2020-10-13 |  | 168000
Contra Costa | BART | CC-170060 | 6861 | RIP-T5-18-FED-CC | RTIP | RTIP-FED |  | 6000 |  | -6000() | CON | Concord BART Station Modernization | [7 empty] | 2021-06-30 | 9500000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 9500000 |  |  |  | 9500000 | 9500000 | 8/26 - BART will likely seek an allocation extension per discussion with BART staff and Karl Anderson. |  |  |  |  | 2020-09-30 |  | 9500000
Contra Costa | Contra Costa County | VAR170002 | 6460 | H8-04-006 | HSIP 8 | HSIP | HSIPL | 5928 | 140 | HSIPL-5928(140) | CON | Danville Blvd/Orchard Ct Comp Streets H8- |  |  | Ext to 4/30/21 | 2019-12-09 | 2022-04-01 |  |  | 2021-04-30 | 2233000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 2233000 | [5 empty] | 2233000 | 2233000 | 9/1 - The County intends to ask for a time extension due to the COVID virus and has discuss with with Caltrans Local Assistance. They requested us to wait and request this extension closer to the obligation deadline, somewhere in the January time period. 8/26 - ROW extended? Requested confirmation from CCTA. |  |  | 19/20 | 19/20 | 2020-09-30 |  | 2233000
Contra Costa | Contra Costa County | VAR170002 | 6462 | H8-04-008 | HSIP 8 | HSIP | HSIPL | 5928 | 143 | HSIPL-5928(143) | CON | Byron Highway/Byer Road Safety |  |  | Ext to 4/30/21 | 2019-12-09 | 2021-05-01 | 2017-06-22 |  | 2021-04-30 | 508230 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 508230 | [5 empty] | 508230 | 508230 | 9/1 - The County intends to ask for a time extension due to the COVID virus and has discuss with with Caltrans Local Assistance. They requested us to wait and request this extension closer to the obligation 8/26 - ROW extended? Requested confirmation from CCTA. |  |  | 19/20 | 19/20 | 2020-09-30 |  | 508230
Contra Costa | Contra Costa County | VAR170002 | 6972 | H9-04-009 | HSIP 9 | HSIP |  | 5928 |  | -5928() | CON | H9-04-009 Kirker Pass Road Safety Improvements |  |  |  |  | 2021-05-01 | 2019-07-22 |  | 2021-12-31 | 1051000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1051000 | [5 empty] | 1051000 | 1051000 | 8/26 - Project will obligated in FFY20/21. Need to change in FMS to 2021 6/6 - Deadline 12/31/21? |  |  |  |  | 2020-09-30 |  | 1051000
Contra Costa | Contra Costa County | VAR170002 | 6973 | H9-04-010 | HSIP 9 | HSIP | HSIPL | 5928 | 157 | HSIPL-5928(157) | CON | H9-04-010 Crockett Area Guardrail Upgrades |  |  |  |  | 2021-04-28 | 2019-07-19 |  | 2021-12-31 | 999963 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 999963 | [5 empty] | 999963 | 999963 | 8/26 - Project will obligated in FFY20/21. Need to change in FMS to 2021 6/6 - Deadline 12/31/21? |  |  |  |  | 2020-09-30 |  | 999963
Contra Costa | Contra Costa County | CC-170020 | 6507 | ATP-REG-T5-3-FED | ATP-REG | ATP-FED | ATPL | 5928 | 151 | ATPL-5928(151) | CON | Fred Jackson Way First Mile/Last Mile Connection |  |  |  |  | 2021-05-31 | 2018-05-24 |  | 2021-01-31 | 3137000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 3137000 |  |  | 3137000 | 3137000 | 8/26 - County plans to award in May 2021 |  |  |  |  | 2020-09-30 |  | 3137000
Contra Costa | El Cerrito | CC-070046 | 918 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5239 |  | -5239() | PE | El Cerrito del Norte Area TOD Complete Street Imps | [7 empty] | 2021-01-31 | 850000 |  |  | 0 | [6 empty] | 0 |  |  | 850000 | 850000 | [6 empty] | 850000 | 850000 | 9/1 - PSE funds added, but City will need TIP Revision to update funds/FY |  |  |  |  | 2020-09-01 |  | 850000
Contra Costa | Orinda | CC-170032 | 6697 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5444 | 021 | STPL-5444(021) | CON | Orinda Way Pavement Rehabilitation |  |  |  |  | 2021-04-06 | 2019-11-18 |  | 2021-01-31 | 620000 |  |  | 0 | [6 empty] | 0 |  | 620000 |  | 620000 | [6 empty] | 620000 | 620000 | [5 empty] | 2020-09-30 |  | 620000
Contra Costa | Orinda | VAR170012 | 5336 | 28C0331 | HBP-Seismic | Bridge | STPLZ | 5444 | 018 | STPLZ-5444(018) | ROW | Bear Creek Road over San Pablo Creek | [5 empty] | 2018-09-11 |  | 2020-03-01 | 132795 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 132795 |  |  |  |  | 132795 | 132795 | Pending PDA approval |  |  |  |  | 2019-10-01 |  | 132795
Contra Costa | Orinda | VAR170012 | 5336 | 28C0331 | HBP-Seismic | Bridge | STPLZ | 5444 | 018 | STPLZ-5444(018) | CON | Bear Creek Road over San Pablo Creek |  |  |  |  | 2021-07-31 | 2018-09-11 |  | 2020-08-01 | 132795 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 132795 |  |  |  |  | 132795 | 132795 | Pending PDA approval |  |  |  |  | 2019-10-01 |  | 132795
Contra Costa | Orinda | VAR170012 | 5335 | 28C0330 | HBP-Seismic | Bridge | STPLZ | 5444 | 019 | STPLZ-5444(019) | ROW | Miner Road over San Pablo Creek | [7 empty] | 2020-08-01 | 50000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 50000 |  |  |  |  | 50000 | 50000 | Pending PDA approval |  |  |  |  | 2019-10-01 |  | 50000
Contra Costa | Orinda | VAR170012 | 5335 | 28C0330 | HBP-Seismic | Bridge | STPLZ | 5444 | 019 | STPLZ-5444(019) | CON | Miner Road over San Pablo Creek |  |  |  |  | 2021-07-31 | 2018-09-11 |  | 2020-04-01 | 957500 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 957500 |  |  |  |  | 957500 | 957500 | Pending PDA approval |  |  |  |  | 2019-10-01 |  | 957500
Contra Costa | Pinole | CC-170048 | 6767 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5126 | 027 | STPL-5126(027) | CON | Pinole - San Pablo Avenue Rehabilitation |  |  |  |  | 2021-05-01 | 2020-09-24 |  | 2021-01-31 | 586000 |  |  | 0 | [6 empty] | 0 |  | 586000 |  | 586000 | [6 empty] | 586000 | 586000 | 9/22 - FR scheduled for 9/24. Will send FPN when received. 8/26 - Pinole submitted field review package to DLAE on 8/18. Field Review has not been scheduled yet. |  |  |  |  | 2020-09-30 |  | 586000
Contra Costa | Pittsburg | CC-170040 | 6731 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5127 | 036 | CML-5127(036) | CON | Pittsburg BART Pedestrian and Bicycle Connectivity |  |  |  |  | 2020-03-01 | 2018-09-14 |  | 2021-01-31 | 3387000 |  |  | 0 | [6 empty] | 0 |  |  | 3387000 | 3387000 | [6 empty] | 3387000 | 3387000 | [5 empty] | 2020-09-30 |  | 3387000
Contra Costa | Richmond | CC-050076 | 872 | RIP-T4-14-FED-CC | RTIP | RTIP-FED | STPL | 5137 | 050 | STPL-5137(050) | ROW | I-80/Central Avenue - Local Portion |  |  |  |  | 2023-02-01 | 2018-06-05 |  | 2021-06-30 | 2000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 2000000 |  |  |  | 2000000 | 2000000 | 8/26 - The City will be submitting allocation extension request (seeking 9 months extension to March 2022) |  |  |  |  | 2020-09-30 |  | 2000000
Contra Costa | Richmond | CC-050076 | 872 | RIP-T5-18-FED-CC | RTIP | RTIP-FED | STPL | 5137 | 050 | STPL-5137(050) | ROW | I-80/Central Avenue - Local Portion |  |  |  |  | 2023-02-01 | 2018-06-05 |  | 2021-06-30 | 3900000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 3900000 |  |  |  | 3900000 | 3900000 | 8/26 - The City will be submitting allocation extension request (seeking 9 months extension to March 2022) |  |  |  |  | 2020-09-30 |  | 3900000
Contra Costa | San Pablo | CC-150017 | 6280 | ATP-REG-T4-2-FED | ATP-REG | ATP-FED | ATPL | 5137 | 017 | ATPL-5137(017) | CON | Rumrill Blvd Complete Streets Imps |  | 2020-05-01 |  |  | 2021-01-19 | 2016-10-01 |  | 2020-10-31 | 4010000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 4010000 |  |  | 4010000 | 4010000 | 3/23 - Planned allocation October 2020 |  |  |  |  | 2019-10-01 |  | 4010000
Contra Costa | San Pablo | CC-170031 | 6679 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5303 | 022 | STPL-5303(022) | CON | San Pablo - Giant Road Pavement Rehabilitation |  |  |  |  | 2021-04-01 | 2020-08-12 |  | 2021-01-31 | 618000 |  |  | 0 | [6 empty] | 0 |  | 618000 |  | 618000 | [6 empty] | 618000 | 618000 | [5 empty] | 2020-09-30 |  | 618000
Contra Costa | San Pablo | VAR170002 | 6985 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5303 | 020 | HSIPL-5303(020) | CON | Intersection Church/Willow, El Portal/Mission Bell |  |  |  |  | 2021-04-01 | 2019-06-26 |  | 2022-06-30 | 750870 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 750870 | [5 empty] | 750870 | 750870 | [5 empty] | 2020-08-27 |  | 750870
Contra Costa | San Ramon | CC-170045 | 6742 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5437 | 031 | STPL-5437(031) | CON | Alcosta Boulevard Pavement Rehab |  |  |  |  | 2021-04-01 | 2020-01-06 |  | 2021-01-31 | 1175000 |  |  | 0 | [6 empty] | 0 |  | 1175000 |  | 1175000 | [6 empty] | 1175000 | 1175000 | [5 empty] | 2020-09-30 |  | 1175000
Contra Costa | Walnut Creek | CC-170038 | 6716 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5225 | 030 | STPL-5225(030) | CON | Ygnacio Valley Road Rehabilitation |  |  |  |  | 2021-04-21 | 2020-05-12 |  | 2021-01-31 | 2608000 |  |  | 0 | [6 empty] | 0 |  | 2608000 |  | 2608000 | [6 empty] | 2608000 | 2608000 | [5 empty] | 2020-09-30 |  | 2608000
Marin | Corte Madera | MRN170019 | 6520 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5232 | 011 | CML-5232(011) | CON | Corte Madera-Paradise Drive Multiuse Path |  |  |  |  | 2021-08-01 | 2019-12-30 |  | 2021-01-31 | 595000 |  |  | 0 | [6 empty] | 0 |  |  | 595000 | 595000 | [6 empty] | 595000 | 595000 | 9/1 - Project confirmed for FFY20/21. |  |  |  |  | 2020-09-30 |  | 595000
Marin | Marin County | VAR170002 | 6264 | HSIP-T5-7 | HSIP 7 | HSIP | HSIPL | 5927 | 115 | HSIPL-5927(115) | CON | HSIP7-04-011 - Arterials & Collector Sign Upgrades | [7 empty] | 2020-12-31 | 445500 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 445500 | [5 empty] | 445500 | 445500 | [5 empty] | 2020-09-23 |  | 445500
Marin | Marin County | VAR170002 | 6968 | H9-04-017 | HSIP 9 | HSIP | HSIPL | 5927 | 123 | HSIPL-5927(123) | CON | Marin Co-Upgrade Non-Standard Guardrails H9-04-017 |  |  |  |  | 2021-07-01 | 2019-06-04 | 2021-01-31 | 2021-12-31 | 861200 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 861200 | [5 empty] | 861200 | 861200 | 9/1 - Project confirmed for FFY20/21. 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 861200
Marin | Marin County | VAR170002 | 6969 | H9-04-016 | HSIP 9 | HSIP | HSIPL | 5927 | 122 | HSIPL-5927(122) | CON-CE | Countywide Signal Upgrade Project (HSIP9-04-016) |  |  |  |  | 2021-09-01 | 2019-05-14 | 2021-06-01 | 2022-06-30 | 2300200 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 2300200 | [5 empty] | 2300200 | 2300200 | 9/1 - Project confirmed for FFY20/21. 6/6 - Deadline 12/31/21? |  |  |  |  | 2020-09-30 |  | 2300200
Marin | San Anselmo | MRN170020 | 6771 | CMAQ-T5-OBAG2-CA-SRTS | OBAG 2 | CMAQ | CML | 5159 | 024 | CML-5159(024) | CON | San Anselmo Bike Spine |  |  |  |  | 2021-04-01 | 2018-09-26 |  | 2021-01-31 | 228000 |  |  | 0 | [6 empty] | 0 |  |  | 228000 | 228000 | [6 empty] | 228000 | 228000 | 9/1 - Project confirmed for FFY20/21. |  |  |  |  | 2020-09-30 |  | 228000
Marin | San Anselmo | MRN170021 | 6772 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5159 | 025 | STPL-5159(025) | CON | Sir Francis Drake Blvd Pavement Rehabilitation |  |  |  |  | 2021-05-15 | 2019-12-22 |  | 2021-01-31 | 1019000 |  |  | 0 | [6 empty] | 0 |  | 1019000 |  | 1019000 | [6 empty] | 1019000 | 1019000 | 9/1 - Project confirmed for FFY20/21. |  |  |  |  | 2020-09-30 |  | 1019000
Marin | San Rafael | MRN170012 | 6575 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | ATPL | 5043 | 042 | ATPL-5043(042) | CON | Francisco Boulevard East Sidewalk Widening |  |  |  |  | 2020-05-18 | 2013-02-05 |  | 2021-01-31 | 2100000 |  |  | 0 | [6 empty] | 0 |  |  | 2100000 | 2100000 | [6 empty] | 2100000 | 2100000 | 9/1 - Project confirmed for FFY20/21 |  |  |  |  | 2020-09-30 |  | 2100000
Marin | San Rafael | VAR170002 | 6982 | H9-04-030 | HSIP 9 | HSIP | HSIPL | 5043 | 043 | HSIPL-5043(043) | CON | H9-04-030 Third Street Safety Improvements Project |  |  |  |  | 2021-05-17 | 2019-03-22 |  | 2022-06-30 | 1293800 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1293800 | [5 empty] | 1293800 | 1293800 | 9/1 - Project confirmed for FFY20/21 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 1293800
Napa | American Canyon | NAP170006 | 6603 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5470 |  | -5470() | CON | Green Island Road Class I | [7 empty] | 2021-06-30 | 1000000 |  |  | 0 | [6 empty] | 0 |  | 1000000 |  | 1000000 | [6 empty] | 1000000 | 1000000 | [5 empty] | 2020-09-30 |  | 1000000
Napa | Napa County | NAP170008 | 6604 | STP-T5-OBAG2-REG-PCA | OBAG 2 | STP |  | 5921 | 083 | -5921(083) | CON | Silverado Trail Phase L Rehab |  |  |  |  | 2021-07-06 | 2020-07-30 |  | 2021-01-31 | 689000 |  |  | 0 | [6 empty] | 0 |  | 689000 |  | 689000 | [6 empty] | 689000 | 689000 | [5 empty] | 2020-09-30 |  | 689000
Napa | NVTA | NAP150003 | 6281 | ATP-REG-T4-2-FED | ATP-REG | ATP-FED | ATPL | 6429 |  | ATPL-6429() | CON | Napa Valley Vine Trail - St. Helena to Calistoga |  |  |  |  | 2020-07-09 | 2019-09-11 |  | 2021-02-28 | 6106000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 6106000 |  |  | 6106000 | 6106000 | 9/10 - Plan to allocate at March 2021 meeting NVTA will request 20 month extension |  |  |  |  | 2019-10-01 |  | 6106000
Napa | NVTA | NAP150003 | 6281 | STP-T5-OBAG2-REG-PCA | OBAG 2 | STP |  | 6429 |  | -6429() | CON | Napa Valley Vine Trail - St. Helena to Calistoga |  |  |  |  | 2020-07-09 | 2019-09-11 |  | 2021-01-31 | 711000 |  |  | 0 | [6 empty] | 0 |  | 711000 |  | 711000 | [6 empty] | 711000 | 711000 | 9/10 - Plan to allocate at March 2021 meeting |  |  |  |  | 2020-09-30 |  | 711000
Napa | MTC | NAP190007 | 7162 | STP-T5-OBAG2-REG-AOM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | Napa Valley Forward: Traffic Calming & Mutlimodal | [7 empty] | 2021-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  | 1000000 |  | 1000000 | [6 empty] | 1000000 | 1000000 | [5 empty] | 2020-09-30 |  | 1000000
Region | MTC | MTC050001 | 1608 | CMAQ-T5-OBAG2-REG-AOM | OBAG 2 | CMAQ |  | 6084 |  | -6084() | CON | Bay Area Commuter Benefits Program | [7 empty] | 2021-01-31 | 406000 |  |  | 0 | [6 empty] | 0 |  |  | 406000 | 406000 | [6 empty] | 406000 | 406000 | [5 empty] | 2020-09-30 |  | 406000
Region | MTC | REG170002 | 6316 | STP-T5-OBAG2-REG-AOM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | Connected Bay Area | [7 empty] | 2021-01-31 | 1840000 |  |  | 0 | [6 empty] | 0 |  | 1840000 |  | 1840000 | [6 empty] | 1840000 | 1840000 | [5 empty] | 2020-09-30 |  | 1840000
Region | MTC | REG170014 | 6642 | STP-T5-OBAG2-REG-AOM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | Active Operations Management | [7 empty] | 2021-01-31 | 9687000 |  |  | 0 | [6 empty] | 0 |  | 9687000 |  | 9687000 | [6 empty] | 9687000 | 9687000 | [5 empty] | 2020-09-30 |  | 9687000
San Francisco | SFDPW | SF-130001 | 5673 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5934 | 185 | -5934(185) | CON | SF - Better Market Street Transportation Elements |  |  | AC Authorized | 2020-09-18 | 2021-06-01 | 2020-07-07 |  | 2021-01-31 | 3366000 |  |  | 0 | [6 empty] | 0 |  | 3366000 |  | 3366000 | [6 empty] | 3366000 | 3366000 | 8/31 - SFCTA confirmed project for FFY20/21 |  |  |  |  | 2020-09-30 |  | 3366000
San Francisco | SFDPW | SF-110005 | 4659 | EARMARK-T5-RE | EARMARK | EARMARK |  | 5934 |  | -5934() | CON | Great Highway Restoration | [7 empty] | 2021-09-30 | 163513 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 163513 | 163513 | 163513 | 8/31 - SFCTA has begun working with SF Planning, SFPW, and SFMTA to identify a project on the corridor or in the general project area that is consistent with the approved scope of work and can obligate funds by the September 2021 deadline. |  |  |  |  | 2020-08-24 |  | 163513
San Francisco | SFMTA | SF-050024 | 2267 | RIP-T5-18-ST-SF | RTIP | RTIP-FED |  |  |  | -() | CON | SFMTA:Train Control & Trolley Signal Rehab/Replace | [7 empty] | 2021-06-30 | 13752000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 13752000 |  |  |  | 13752000 | 13752000 | 9/22 - Karl confirmed these RTIP funds have Federal Funds. Waiting for SFCTA for project dates. |  |  |  |  | 2020-09-22 |  | 13752000
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0001 | HBP-Seismic | Bridge | STPLZ | 6272 | 024 | STPLZ-6272(024) | CON | WB SFOBB on ramp West of YBI |  |  | FY 19 |  |  |  | 2018-11-30 | 2019-10-01 | 369633.9756 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 369633.9756 |  |  |  |  | 369633.9756 | 369633.9756 | [5 empty] | 2019-10-01 |  | 369633.9756
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0002 | HBP-Seismic | Bridge | STPLZ | 6272 | 026 | STPLZ-6272(026) | ROW | WB I-80 on ramp West of Yerba Buena Island |  |  | PAST DUE | PAST DUE |  |  |  | 2019-03-31 | 550000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 550000 |  |  |  |  | 550000 | 550000 | 9/1 - As per phone call with Aprile, ROW should be removed. Check with Ross |  |  |  |  | 2019-10-01 |  | 550000
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0002 | HBP-Seismic | Bridge | STPLZ | 6272 | 026 | STPLZ-6272(026) | CON | WB I-80 on ramp West of Yerba Buena Island |  |  | FY 19 |  |  |  | 2018-11-30 | 2019-10-01 | 19077010.9303 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 19077010.9303 |  |  |  |  | 19077010.9303 | 19077010.9303 | [5 empty] | 2019-10-01 |  | 19077010.9303
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0003 | HBP-Seismic | Bridge | STPLZ | 6272 | 027 | STPLZ-6272(027) | ROW | EB I-80 off ramp to TI Road (2 Bridges) |  |  | PAST DUE | PAST DUE |  |  |  | 2019-03-31 | 300000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 300000 |  |  |  |  | 300000 | 300000 | 9/1 - As per phone call with Aprile, ROW should be removed. Check with Ross |  |  |  |  | 2019-10-01 |  | 300000
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0003 | HBP-Seismic | Bridge | STPLZ | 6272 | 027 | STPLZ-6272(027) | CON | EB I-80 off ramp to TI Road (2 Bridges) |  |  | FY 19 |  |  |  | 2018-11-30 | 2019-10-01 | 8460249.4289 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 8460249.4289 |  |  |  |  | 8460249.4289 | 8460249.4289 | [5 empty] | 2019-10-01 |  | 8460249.4289
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0004 | HBP-Seismic | Bridge | STPLZ | 6272 | 028 | STPLZ-6272(028) | CON | Treasure Island Road West of SFOBB |  |  | FY 19 |  |  |  | 2018-11-30 | 2019-10-01 | 1724961.1255 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 1724961.1255 |  |  |  |  | 1724961.1255 | 1724961.1255 | [5 empty] | 2019-10-01 |  | 1724961.1255
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0006 | HBP-Seismic | Bridge | STPLZ | 6272 | 029 | STPLZ-6272(029) | CON | Hillcrest Road West of Yerba Buena Island |  |  | PAST DUE | PAST DUE |  |  | 2018-11-30 | 2017-06-30 | 2042843.2572 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 2042843.2572 |  |  |  |  | 2042843.2572 | 2042843.2572 | [5 empty] | 2019-10-01 |  | 2042843.2572
San Francisco | SFCTA | SF-070027 | 3741 | 01CA007A | HBP-Seismic | Bridge | STPLZ | 6272 | 030 | STPLZ-6272(030) | CON | Treasure Island Road West of SFOBB |  |  | FY 19 |  |  |  | 2018-11-30 | 2019-10-01 | 271062.3426 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 271062.3426 |  |  |  |  | 271062.3426 | 271062.3426 | [5 empty] | 2019-10-01 |  | 271062.3426
San Francisco | SFCTA | SF-070027 | 3741 | 01CA007B | HBP-Seismic | Bridge | STPLZ | 6272 | 031 | STPLZ-6272(031) | CON | Treasure Isand Road west of SFOBB |  |  | FY 19 |  |  |  | 2018-11-30 | 2019-10-01 | 357315.4159 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 357315.4159 |  |  |  |  | 357315.4159 | 357315.4159 | [5 empty] | 2019-10-01 |  | 357315.4159
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0008 | HBP-Seismic | Bridge | STPLZ | 6272 | 032 | STPLZ-6272(032) | CON | Treasure Island road West of SFOBB |  |  | FY 19 |  |  |  | 2018-11-30 | 2019-10-01 | 505169.0061 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 505169.0061 |  |  |  |  | 505169.0061 | 505169.0061 | [5 empty] | 2019-10-01 |  | 505169.0061
San Francisco | SFCTA | SF-070027 | 3741 |  | HBP-Seismic | Bridge | STPLZ | 6272 | 046 | STPLZ-6272(046) | ROW | Yerba Buena Island (YBI) Ramp Improvements |  |  | AC Authorized | 2020-07-29 |  |  |  | 2020-09-30 | 338185 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 338185 |  |  |  |  | 338185 | 338185 | 9/1 - Ramps are for all YBI projects. Received E-76 in 2013 for ROW |  |  |  |  | 2020-04-10 |  | 338185
San Mateo | Atherton | SM-190008 | 7040 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5261 |  | -5261() | CON | Atherton Street Preservation |  |  |  |  | 2021-01-15 | 2019-11-01 |  | 2021-01-31 | 251000 |  |  | 0 | [6 empty] | 0 |  | 251000 |  | 251000 | [6 empty] | 251000 | 251000 | 8/31 - Todd confirmed projects for FFY 20/21 |  |  |  |  | 2020-09-30 |  | 251000
San Mateo | Belmont | SM-170042 | 6658 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5268 |  | -5268() | CON | Ralston Avenue Corridor Bike-Ped Imps |  |  |  |  | 2021-05-15 | 2019-03-01 |  | 2021-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  |  | 1000000 | 1000000 | [6 empty] | 1000000 | 1000000 | 8/31 - Todd confirmed projects for FFY 20/21 |  |  |  |  | 2020-09-30 |  | 1000000
San Mateo | Burlingame | SM-170015 | 6649 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5171 |  | -5171() | CON | Hoover School Area Sidewalk Impvts (Summit Dr.) |  |  |  |  | 2021-05-15 | 2018-07-11 |  | 2021-01-31 | 700000 |  |  | 0 | [6 empty] | 0 |  |  | 700000 | 700000 | [6 empty] | 700000 | 700000 | 8/31 - Todd confirmed projects for FFY 20/21 |  |  |  |  | 2020-09-30 |  | 700000
San Mateo | Hillsborough | SM-170026 | 6696 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5191 |  | -5191() | CON | Hillsborough Street Resurfacing |  |  |  |  | 2021-04-15 | 2020-07-29 |  | 2021-01-31 | 408000 |  |  | 0 | [6 empty] | 0 |  | 408000 |  | 408000 | [6 empty] | 408000 | 408000 | 8/31 - Todd confirmed projects for FFY 20/21 |  |  |  |  | 2020-09-30 |  | 408000
San Mateo | San Mateo | SM-170039 | 6616 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5102 |  | -5102() | CON | Laurie Meadows Ped/Bike Safety Improvements |  |  |  |  | 2021-02-15 | 2020-08-15 |  | 2021-01-31 | 987000 |  |  | 0 | [6 empty] | 0 |  |  | 987000 | 987000 | [6 empty] | 987000 | 987000 | 8/31 - Todd confirmed projects for FFY 20/21 |  |  |  |  | 2020-09-30 |  | 987000
San Mateo | San Mateo County | SM-170014 | 6628 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5935 | 081 | -5935(081) | CON | San Mateo Countywide Pavement Maintenance |  |  |  |  | 2021-05-15 | 2020-09-19 |  | 2021-01-31 | 965000 |  |  | 0 | [6 empty] | 0 |  | 965000 |  | 965000 | [6 empty] | 965000 | 965000 | 8/31 - Todd confirmed projects for FFY 20/21 |  |  |  |  | 2020-09-30 |  | 965000
San Mateo | SMCCAG | SM-070002 | 2561 | RIP-T4-12-FED-SM | RTIP | RTIP-FED |  | 6419 |  | -6419() | CON | San Mateo Countywide ITS Improvements |  |  |  |  | 2021-06-15 | 2018-05-16 |  | 2020-01-31 | 4058000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 4058000 |  |  |  | 4058000 | 4058000 | 8/31 - Todd confirmed projects for FFY 20/21 |  |  |  |  | 2020-08-31 |  | 4058000
San Mateo | South San Francisco | VAR170002 | 6991 | HSIP-T5-9 | HSIP 9 | HSIP |  | 5177 | 043 | -5177(043) | CON | Ped. Imp. On W. Orange and Hillsdale (H9-04-031) |  |  |  |  | 2021-03-15 | 2019-08-07 |  | 2022-06-30 | 204800 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 204800 | [5 empty] | 204800 | 204800 | 8/31 - Todd confirmed projects for FFY 20/21 |  |  |  |  | 2020-08-31 |  | 204800
Santa Clara | Los Altos | SCL170038 | 6678 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5309 | 019 | STPL-5309(019) | CON | Los Altos: Fremont Ave Pavement Preservation |  |  |  |  | 2021-02-23 | 2019-11-19 |  | 2021-01-31 | 336000 |  |  | 0 | [6 empty] | 0 |  | 336000 |  | 336000 | [6 empty] | 336000 | 336000 | 7/1 - City completed FR on 11/19. Requested FPN from City. |  |  |  |  | 2020-09-30 |  | 336000
Santa Clara | Milpitas | SCL170039 | 6672 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5314 | 011 | STPL-5314(011) | CON | Street Resurfacing 2020 & 2021 |  |  |  |  | 2020-05-31 |  |  | 2021-01-31 | 578358 |  |  | 0 | [6 empty] | 0 |  | 578358 |  | 578358 | [6 empty] | 578358 | 578358 | 10/7 - Partial obligation in FFY19/20. TIP Programming change for balance in FFY20/21 |  |  |  |  | 2021-09-30 |  | 578358
Santa Clara | San Jose | SCL050083 | 1949 | ATP-REG-T4-1-FED | ATP-REG | ATP-FED | ATPL | 5005 | 146 | ATPL-5005(146) | CON | Coyote Creek Trail: Mabury to Empire | [7 empty] | 2021-02-28 | 4046000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 4046000 |  |  | 4046000 | 4046000 | 6/26 - Will allocate by deadline Working with CTC and Karl on extension. |  |  |  |  | 2019-10-01 |  | 4046000
Santa Clara | San Jose | SCL170061 | 6752 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5005 | 162 | CML-5005(162) | PE | W San Carlos Urban Village Streets Improvements |  |  | AC Authorized | 2020-08-26 |  |  |  | 2021-01-31 | 2618000 |  |  | 0 | [6 empty] | 0 |  |  | 2618000 | 2618000 | [6 empty] | 2618000 | 2618000 | 6/26 - Will obligate FFY20/21. FR on 9/13/19 |  |  |  |  | 2020-09-30 |  | 2618000
Santa Clara | San Jose | SCL170044 | 6652 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5005 | 163 | STPL-5005(163) | CON | San Jose Pavement Maintenance |  |  | AC Conversion at CT-HQ | 2020-09-02 |  |  |  | 2020-06-30 | 14159062 |  |  | 0 | [6 empty] | 0 |  | 14159062 |  | 14159062 | [6 empty] | 14159062 | 14159062 | 5/6 - Request for project RFA update |  |  |  |  | 2020-04-14 |  | 14159062
Santa Clara | San Jose | SCL170029 | 6647 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5005 | 155 | CML-5005(155) | CON | Tully Road Safety Improvements |  |  |  |  | 2021-06-30 | 2018-08-20 |  | 2021-01-31 | 5975360 |  |  | 0 | [6 empty] | 0 |  |  | 5975360 | 5975360 | [6 empty] | 5975360 | 5975360 | 6/26 - Will obligate FFY20/21 - FR on 8/20/18 |  |  |  |  | 2020-09-30 |  | 5975360
Santa Clara | San Jose | SCL170029 | 6647 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5005 | 155 | -5005(155) | CON | Tully Road Safety Improvements |  |  |  |  | 2021-06-30 | 2018-08-20 |  | 2021-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  | 1000000 |  | 1000000 | [6 empty] | 1000000 | 1000000 | 6/26 - Will obligate FFY20/21 - FR on 8/20/18 |  |  |  |  | 2020-09-30 |  | 1000000
Santa Clara | San Jose | SCL170030 | 6648 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5005 | 154 | -5005(154) | CON | McKee Road Safety Improvements |  |  |  |  | 2021-06-30 | 2020-08-10 |  | 2021-01-31 | 6994933 |  |  | 0 | [6 empty] | 0 |  | 6994933 |  | 6994933 | [6 empty] | 6994933 | 6994933 | 6/26 - Will obligate FFY20/21 - FR on 8/10/18 |  |  |  |  | 2020-09-30 |  | 6994933
Santa Clara | Sunnyvale | SCL170059 | 6829 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5213 |  | ATPL-5213() | PSE | Sunnyvale Safe Routes to School Imps |  |  | CTC Ext Approved | 2019-05-15 |  |  |  | 2020-01-31 | 318000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 318000 |  |  | 318000 | 318000 | 8/27 - Was extension approved? 3/23 -Requesting CON extension to FY22 at May meeting |  |  |  |  | 2019-10-01 |  | 318000
Santa Clara | Sunnyvale | SCL170059 | 6829 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5213 |  | ATPL-5213() | CON | Sunnyvale Safe Routes to School Imps | [7 empty] | 2020-01-31 | 1509000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 1509000 |  |  | 1509000 | 1509000 | 8/27 - Moved to FY2022? 3/23 -Requesting CON extension to FY22 at May meeting |  |  |  |  | 2019-10-01 |  | 1509000
Santa Clara | Sunnyvale | SCL170017 | 6555 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5213 | 068 | ATPL-5213(068) | CON-CE | Sunnyvale SNAIL Neighborhood Improvements | [7 empty] | 2020-01-31 | 13000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 13000 |  |  | 13000 | 13000 | 8/27 - Construction funding deferred to FY2023 |  |  |  |  | 2019-10-01 |  | 13000
Santa Clara | Sunnyvale | SCL170017 | 6555 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5213 | 068 | ATPL-5213(068) | PSE | Sunnyvale SNAIL Neighborhood Improvements | [7 empty] | 2020-01-31 | 780000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 780000 |  |  | 780000 | 780000 | 8/27 - Construction funding deferred to FY2023 3/23 - Requesting Extension to FY21 at May meeting |  |  |  |  | 2019-10-01 |  | 780000
Santa Clara | Sunnyvale | SCL170017 | 6555 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED |  | 5213 |  | -5213() | CON | Sunnyvale SNAIL Neighborhood Improvements | [7 empty] | 2020-01-31 | 3982000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 3982000 |  |  | 3982000 | 3982000 | 8/27 - Construction funding deferred to FY2023 |  |  |  |  | 2020-09-30 |  | 3982000
Santa Clara | Sunnyvale | VAR170002 | 7002 | H9-04-034 | HSIP 9 | HSIP |  | 5213 |  | -5213() | CON | H9-04-034 Advanced Dilemma Zone Detection Phase 2 | [7 empty] | 2022-06-30 | 1112000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1112000 | [5 empty] | 1112000 | 1112000 | 8/27 - Execution of construction contract underway. 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 1112000
Santa Clara | Sunnyvale | SCL170025 | 6619 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5213 |  | -5213() | CON | Fair Oaks Avenue Bikeway - Phase 2 | [7 empty] | 2021-01-31 | 447000 |  |  | 0 | [6 empty] | 0 |  |  | 447000 | 447000 | [6 empty] | 447000 | 447000 | [5 empty] | 2020-09-30 |  | 447000
Santa Clara | Sunnyvale | SCL170027 | 6632 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5213 |  | -5213() | CON | Sunnyvale Traffic Signal Upgrades/Replacements | [7 empty] | 2021-01-31 | 2366000 |  |  | 0 | [6 empty] | 0 |  | 2366000 |  | 2366000 | [6 empty] | 2366000 | 2366000 | [5 empty] | 2020-09-30 |  | 2366000
Santa Clara | Sunnyvale | SCL170043 | 6763 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ |  | 5213 |  | -5213() | CON | Homestead Rd at Homestead High School Improvements | [7 empty] | 2021-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  |  | 1000000 | 1000000 | [6 empty] | 1000000 | 1000000 | [5 empty] | 2020-09-30 |  | 1000000
Santa Clara | VTA | SCL090030 | 4197 | RIP-T5-18-ST-SCL | RTIP | RTIP-ST |  | 6264 |  | -6264() | ROW | SR 85 Express Lanes | [7 empty] | 2020-01-31 | 600000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 600000 |  |  |  | 600000 | 600000 | 9/21 - State Funds, remove from AOP 8/4 - Civil is ongoing. The funds were allocated at 5/15/19 CTC meeting |  |  |  |  | 2020-09-30 |  | 600000
Santa Clara | VTA | SCL090030 | 4197 | RIP-T5-18-ST-SCL | RTIP | RTIP-ST |  | 6264 |  | -6264() | CON | SR 85 Express Lanes | [7 empty] | 2020-01-31 | 2300000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 2300000 |  |  |  | 2300000 | 2300000 | 9/21 - State Funds, remove from AOP 8/4 - Civil was extended 12 months (to 6/30/21) and was approved at 5/13/20 CTC meeting 3/31 - VTA is seeking an extension until 6/30/2021 10/8 VTA may seek extension at May 20 CTC meeting. |  |  |  |  | 2020-09-30 |  | 2300000
Santa Clara | VTA | SCL150001 | 6045 | RIP-T4-14-FED-SCL | RTIP | RTIP-FED | RPSTPL | 6264 |  | RPSTPL-6264() | PSE | I-680 Soundwalls - Capitol Expwy to Mueller Ave |  |  | CTC Ext Approved | 2018-06-28 |  |  | 2018-01-31 | 2018-01-31 | 731000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 731000 |  |  |  | 731000 | 731000 | 8/4 - is ongoing. Expecting to finish by early 2021 |  |  |  |  | 2019-10-01 |  | 731000
Santa Clara | VTA | SCL150001 | 6045 | RIP-T4-14-FED-SCL | RTIP | RTIP-FED |  | 6264 |  | -6264() | CON | I-680 Soundwalls - Capitol Expwy to Mueller Ave | [7 empty] | 2021-01-31 | 3275000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 3275000 |  |  |  | 3275000 | 3275000 | 8/4 - scheduled to be obligated by 6/30/2021. |  |  |  |  | 2020-09-30 |  | 3275000
Santa Clara | VTA | SCL110002 | 4198 | RIP-T5-20-ST-SCL | RTIP | RTIP-ST |  | 6264 |  | -6264() | ROW | Silicon Valley Express Lanes Program - Phase 5 Civil | [7 empty] | 2021-01-31 | 4754000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 4754000 |  |  |  | 4754000 | 4754000 | 9/21 - State Funds, remove from AOP 8/4 - programmed for FY20/21 but has not been allocated |  |  |  |  | 2020-09-30 |  | 4754000
Solano | Fairfield | SOL170006 | 6536 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5132 |  | ATPL-5132() | CON | East Tabor Tolenas SR2S Sidewalk Closure Gap | [7 empty] | 2021-01-31 | 1440000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 1440000 |  |  | 1440000 | 1440000 | 9/18 - Planned to Allocate in June 2021 3/23 - Move to FY21 Obligation Plan |  |  |  |  | 2019-10-01 |  | 1440000
Solano | Rio Vista | VAR170002 | 7008 | H9-04-026 | HSIP 9 | HSIP |  | 5099 |  | -5099() | CON | Rio Vista: H9-04-026 Pedestrian Crossings |  |  |  |  | 2021-05-31 | 2020-05-14 |  | 2022-06-30 | 204600 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 204600 | [5 empty] | 204600 | 204600 | 9/16 - City will obligate funds in FFY20/21 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 204600
Solano | Solano County | SOL170015 | 6719 | STP-T5-OBAG2-CO-FAS | OBAG 2 | STP | STPL | 5923 | 126 | STPL-5923(126) | CON | Solano County Roadway Preservation |  |  |  |  | 2021-01-31 | 2020-05-07 |  | 2020-01-31 | 506000 |  |  | 0 | [6 empty] | 0 |  | 506000 |  | 506000 | [6 empty] | 506000 | 506000 | 9/18 - Project will deliver in FFY20/21 5/6 - Request for project RFA update |  |  |  |  | 2019-10-01 |  | 506000
Solano | Solano County | SOL170016 | 6706 | STP-T5-OBAG2-CO-FAS | OBAG 2 | STP | STPL | 5923 | 123 | STPL-5923(123) | CON | Solano County Farm to Market Phase 3 |  |  |  |  | 2021-01-31 | 2013-11-06 |  | 2021-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  | 1000000 |  | 1000000 | [6 empty] | 1000000 | 1000000 | 9/18 - Project will deliver in FFY20/21 |  |  |  |  | 2020-09-30 |  | 1000000
Solano | Solano County | SOL170016 | 6706 | STP-T5-OBAG2-REG-PCA | OBAG 2 | STP | STPL | 5923 | 123 | STPL-5923(123) | CON | Solano County Farm to Market Phase 3 |  |  |  |  | 2021-01-31 | 2013-11-06 |  | 2021-01-31 | 1918000 |  |  | 0 | [6 empty] | 0 |  | 1918000 |  | 1918000 | [6 empty] | 1918000 | 1918000 | 9/18 - Project will deliver in FFY20/21 |  |  |  |  | 2020-09-30 |  | 1918000
Solano | STA | SOL170009 | 6651 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 6249 | 046 | CML-6249(046) | CON | Solano Mobility Call Center |  |  |  |  | 2021-01-31 |  |  | 2021-01-31 | 300000 |  |  | 0 | [6 empty] | 0 |  |  | 300000 | 300000 | [6 empty] | 300000 | 300000 | [5 empty] | 2020-09-30 |  | 300000
Solano | Suisun City | SOL170014 | 6807 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5032 | 034 | -5032(034) | CON | New Railroad Avenue Pavement Rehabilitation |  |  |  |  | 2021-06-30 | 2019-07-24 |  | 2020-01-31 | 491000 |  |  | 0 | [6 empty] | 0 |  | 491000 |  | 491000 | [6 empty] | 491000 | 491000 | 9/18 - Project will deliver in FFY20/21 5/6 - Request for project RFA update |  |  |  |  | 2019-10-01 |  | 491000
Sonoma | Petaluma | SON170011 | 6615 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5022 | 060 | STPL-5022(060) | CON | Petaluma Blvd South Road Diet at E Street |  |  |  |  | 2020-05-01 | 2018-09-24 |  | 2021-01-31 | 2630000 |  |  | 0 | [6 empty] | 0 |  | 2630000 |  | 2630000 | [6 empty] | 2630000 | 2630000 | 8/17 - City confirmed project will remain in FFY 20/21 |  |  |  |  | 2020-09-30 |  | 2630000
Sonoma | Santa Rosa | SON170012 | 6614 | CMAQ-T4-2-OBAG | OBAG 1 | CMAQ | CML | 5028 | 083 | CML-5028(083) | PE | Highway 101 Bicycle and Pedestrian Bridge |  |  |  |  | 2020-12-01 | 2020-07-15 |  | 2021-01-31 | 364000 |  |  | 0 | [6 empty] | 0 |  |  | 364000 | 364000 | [6 empty] | 364000 | 364000 | 8/31 - City confirmed FFY 20/21, but must provide FR and award dates. 8/17 - FR - 9/24/18, ENV - 10/1/20, CON Adv - 3/1/20 |  |  |  |  | 2020-09-30 |  | 364000
Sonoma | Santa Rosa | SON170012 | 6614 | CMAQ-T5-OBAG2-CO | OBAG 2 | SMAQ | CML | 5028 | 083 | CML-5028(083) | PE | Highway 101 Bicycle and Pedestrian Bridge |  |  |  |  | 2020-12-01 | 2020-07-15 |  | 2021-01-31 | 1418000 |  |  | 0 | [6 empty] | 0 |  |  | 1418000 | 1418000 | [6 empty] | 1418000 | 1418000 | 8/31 - City confirmed FFY 20/21, but must provide FR and award dates. |  |  |  |  | 2020-09-30 |  | 1418000
Sonoma | Sonoma City | SON170022 | 6608 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5114 | 020 | CML-5114(020) | CON | Fryer Creek Pedestrian and Bicycle Bridge |  |  |  |  | 2021-06-28 | 2019-07-10 |  | 2021-01-31 | 501000 |  |  | 0 | [6 empty] | 0 |  |  | 501000 | 501000 | [6 empty] | 501000 | 501000 | 8/31 - Project confirmed to remain in FFY20/21 |  |  |  |  | 2020-09-30 |  | 501000
Sonoma | Sonoma County | VAR170012 | 5253 | 20C0262 | HBP-Seismic | Bridge | STPLZ | 5920 | 059 | STPLZ-5920(059) | CON | Boyes Blvd over Sonoma Creek |  |  | Obligated | 2020-08-31 | 2020-08-31 |  | 2019-04-30 | 2018-11-01 | 3259451 |  |  | 0 |  | 1229020 |  |  |  |  | 1229020 |  |  |  | 0 |  | 4488471 |  |  |  |  | 4488471 | 3259451 | [5 empty] | 2019-10-01 |  | 4488471
Sonoma | Sonoma County | VAR170012 | 5242 | 20C0155 | HBP-Seismic | Bridge | STPLZ | 5920 | 137 | STPLZ-5920(137) | CON | Big Wohler Road over Russian River |  |  | RFA at CT-HQ | 2020-05-20 | 2021-08-31 |  | 2020-10-01 | 2019-11-01 | 3718260 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 3718260 |  |  |  |  | 3718260 | 3718260 | [5 empty] | 2019-10-01 |  | 3718260
Sonoma | Windsor | SON170001 | 6313 | STP-T5-OBAG2-CO | OBAG 2 | STP | CML | 5472 | 021 | CML-5472(021) | CON | Windsor River Road/Windsor Road Intersection Imps |  |  |  |  | 2021-02-01 | 2019-08-01 |  | 2021-01-31 | 3000000 |  |  | 0 | [6 empty] | 0 |  | 3000000 |  | 3000000 | [6 empty] | 3000000 | 3000000 | 9/10 - FR and award dates were updated 7/2 - FR was on 2/11/19 |  |  |  |  | 2020-07-01 |  | 3000000
[21 empty] | 283786620.4821 | 0 | 0 | 0 | 0 | 1229020 | 0 | 0 | 0 | 0 | 1229020 | 0 | 66690353 | 22876360 | 89566713 | 11965163 | 43476251.4821 | 96779000 | 43065000 | 0 | 163513 | 285015640.4821 | 283786620.4821 | [7 empty] | 285015640.4821
J:\PROJECT\Funding\T5-FAST\STP-CMAQ\Obligations and Delivery\Annual Obligation Plans\FY 2020-21\[FFY 2020-21 Annual Obligation Plan.xlsx]FFY 2020-21 9.28 | [32 empty] | 35047658 | 50207348 | 85255006
108
Brought over from FFY19/20 | [23 empty] | 106856993
Remove from FFY20/21 AOP | [20 empty] | 2006820 |  | #REF! | 106856993
Confirmed for FFY20/21 AOP | [22 empty] | 25000000 | [19 empty] | 12/13 - SJ needs to work with MTC on TIP Revision
Sponsor has not responded and will remove upon final submission to CT | [19 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
Wants to move out, but needs to address Inactive Obligations for TIP programming change. | [22 empty] | 0
Follow up for FR, Award date, or more info by 9/23 | [22 empty] | #REF!
Extension CTC extension request | [20 empty] | #REF! |  | #REF!
#REF!
#REF!
123556965
[21 empty] | #REF! | #REF! | #REF! | #REF!
#REF!
Note on N12: John Saelee: May '20: $2.445M of STIP allocated to AlamedaCTC for ROW, State-Only. Caltrans is implementing the Con phase. August '20: $16.816M STIP (and $4.152M ATP) allocated to Caltrans for Phase 1 (2323A) Con, starting 12/2020. Phase 2 (2323B) allocation of $19.523M balance is Est. Dec 2020 w/ Con start: 4/2021.