## FFY 2021-22 Sep 30
MTC FFY 2021-22 Annual Obligation Plan | [43 empty] | Remarks | Field Review (mm/dd/yy) | RFA Submission (EDS or Actual) (mm/dd/yy) | TIP Prog Year | Conf in Plan
Project List | [20 empty] | Remaining | 106173979 | 72622181 | 178796160 |  | Obligations |  |  |  |  | Total |  | 106173979 | 72622181 | 178796160 |  | Fund Type |  |  |  |  | Total | Remaining | [7 empty] | Total
2021-09-30 | [12 empty] | CTC Allocation |  | Obligation | [5 empty] | Balance | STP | CMAQ | STP/CMAQ | HSIP | HBP | RTIP | ATP | SB1 | Other-Fed | Obligations |  | STP | CMAQ | STP/CMAQ | HSIP | HBP | RTIP | ATP | SB1 | OTHER-FED | Programmed | Balance | Enter comments or additional information. Provide contact names & phone numbers or email addresses for questions. | [6 empty] | Programmed
County | Local Agency | TIP ID | FMS ID | Unique ID | Program | Fund Source | FPN | FPN | FPN | FPN | Phase | Project Title | Latest Action | CTC Allocation | Latest Action | Latest Action | Planned | Planned or | Planned | Oblig/Alloc | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Oblig | 27.75% | 4.907% | 32.66% | 9.912% | 16.66% | 21.74% | 8.195% | 0% | 10.83% | 100% | 100% | [5 empty] | Dated Added | Entered in | 100%
[13 empty] | Status | Date | Status | Date | Award | Field Review | Oblig | Deadline | 334371501.0221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Date | 92802159 | 16406893 | 109209052 | 33143150 | 55706180.4821 | 72694490 | 27402000 | 0 | 36216628.54 | 334371501.0221 | 334371501.0221 | [5 empty] | to Plan | FMS | 334371501.0221
County | Sponsor | TIP ID | FMS ID | Unique ID | Program | Fund Source | Prefix | LoCode | Proj # | FPN | Phase | Project Title | Latest Action | CTC Allocation | Latest Action | Action Date | Planned Award | Field Review | Planned Oblig | Deadline | Balance | STP | CMAQ | STP/CMAQ | HSIP | Seismic | RTIP | ATP | SB1 | EARMARK | Oblig Amount | Oblig Date | STP | CMAQ | STP/CMAQ | HSIP | Seismic | STIP | ATP | SB1 | EARMARK | Total | Balance | Remarks | Field Review | RFA | Prog Year | Resp'd? | Dated Added | DATE | Total
Alameda | Alameda | ALA170049 | 6539 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED |  | 5014 | 047 | -5014(047) | PSE | Central Avenue Safety Improvements | Ext to 12/31/21 | 2021-12-31 |  |  | 2022-09-01 | 4/2020 (PID) | 2021-12-31 | 2021-12-31 | 300000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 300000 |  |  | 300000 | 300000 | 8/30 - Incldue in FFY21/22 AOP 3/2 - MTC submitted extension request to CTC on 3/1 8/28 - Project will be moved out to FFY 21/22. Waiting for CTC Action |  |  |  |  | 2020-09-30 |  | 300000
Alameda | Alameda | ALA170074 | 6760 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5014 | 048 | STPL-5014(048) | CON | Alameda City-Wide Pavement Rehabilitation |  |  |  |  | 2022-06-30 | 2021-07-22 | 2022-03-01 | 2022-01-31 | 827000 |  |  | 0 | [6 empty] | 0 |  | 827000 |  | 827000 | [6 empty] | 827000 | 827000 | 8/11 - FR completed and going out for bid in early 2022 and construction in summer 2022. 3/2 - Jacki requested status update |  |  |  |  | 2020-09-30 |  | 827000
Alameda | Alameda County | VAR170002 | 6989 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5933 | 152 | HSIPL-5933(152) | CON | Alameda Co Unsignalized Intersection ImpsH9-04-001 |  |  |  |  | 2022-12-01 | 2021-03-21 | 2022-09-30 | 2022-06-30 | 1750000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1750000 | [5 empty] | 1750000 | 1750000 | 8/31/21 - The County requested an extension to 9/30/22. Awaiting CT confirmation. |  |  |  |  | 2021-09-30 |  | 1750000
Alameda | Alameda County | VAR170002 | 6990 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5933 | 153 | HSIPL-5933(153) | CON | Alameda Co-Signalized Intersection Imps H9-04-002 |  |  |  |  | 2022-12-01 | 2021-03-21 | 2022-12-01 | 2022-06-30 | 2293900 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 2293900 | [5 empty] | 2293900 | 2293900 | 8/31/21 - The County requested an extension to 9/30/22. Awaiting CT confirmation. |  |  |  |  | 2021-09-30 |  | 2293900
Alameda | Alameda County | VAR170002 | 6988 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5933 | 154 | HSIPL-5933(154) | CON | H9-04-003 Alameda County Rural Roads Safety Imps |  |  |  |  | 2023-05-01 | 2021-06-10 | 2022-11-01 | 2022-06-30 | 1330000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1330000 | [5 empty] | 1330000 | 1330000 | 8/31/21 - The County requested an extension to 9/30/22. Awaiting CT confirmation. |  |  |  |  | 2021-09-30 |  | 1330000
Alameda | Alameda County | VAR170002 | 6987 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5933 | 155 | HSIPL-5933(155) | CON | H9-04-004 Tesla Road Safety Improvements |  |  |  |  | 2022-04-01 | 2020-12-22 | 2021-11-15 | 2022-06-30 | 384300 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 384300 | [5 empty] | 384300 | 384300 | 8/31/21 - The County requested an extension to 9/30/22. Awaiting CT confirmation. |  |  |  |  | 2021-09-30 |  | 384300
Alameda | Alameda County | ALA190019 | 7084 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5933 | 143 | -5933(143) |  | Alameda County Complete Street Improvements |  |  |  |  | 2022-05-21 | 2021-09-17 | 2021-12-01 | 2022-09-30 | 2000000 |  |  | 0 | [6 empty] | 0 |  | 2000000 |  | 2000000 | [6 empty] | 2000000 | 2000000 | [5 empty] | 2021-09-30 |  | 2000000
Alameda | ACTC | ALA050079 | 163 | RIP-T5-18-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | CON | I-80 Gilman Interchange Improvements | Allocated | 2021-06-23 |  |  |  | 6/2018 (NEPA) |  | 2020-11-13 | 8979000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 8979000 |  |  |  | 8979000 | 8979000 | 8/30/21 - Caltrans administering Con Phase; CTC allocated June 2021. 3/2 - June CTC allocation by Caltrans |  |  |  |  | 2020-09-30 |  | 8979000
Alameda | ACTC | ALA050079 | 163 | RIP-T5-18-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | CON | I-80 Gilman Interchange Improvements | Allocated | 2020-08-13 |  |  |  | 6/2018 (NEPA) |  | 2020-11-13 | 14360000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 14360000 |  |  |  | 14360000 | 14360000 | 8/30/21 - Caltrans administering Con Phase; CTC allocated June 2021. 3/2 - June CTC allocation by Caltrans |  |  |  |  | 2020-09-30 |  | 14360000
Alameda | ACTC | ALA050079 | 163 | RIP-T5-20-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | CON | I-80 Gilman Interchange Improvements | Allocated | 2021-06-23 |  |  |  | 6/2018 (NEPA) |  | 2020-11-13 | 15445000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 15445000 |  |  |  | 15445000 | 15445000 | 8/30/21 - Caltrans administering Con Phase; CTC allocated June 2021. 3/2 - June CTC allocation by Caltrans |  |  |  |  | 2020-09-30 |  | 15445000
Alameda | ACTC | ALA050079 | 163 | RIP-T5-18-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | ROW | I-80 Gilman Interchange Improvements | Allocated | 2020-05-13 | [6 empty] | 320000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 320000 |  |  |  | 320000 | 320000 | [5 empty] | 2021-08-26 |  | 320000
Alameda | ACTC | ALA050079 | 163 | RIP-T5-18-FED-ALA | RTIP | RTIP-FED |  | 6480 |  | -6480() | ROW | I-80 Gilman Interchange Improvements | Allocated | 2020-05-13 | [6 empty] | 2125000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 2125000 |  |  |  | 2125000 | 2125000 | [5 empty] | 2021-08-26 |  | 2125000
Alameda | ACTC | ALA110033 | 5013 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6480 |  | -6480() | CON | Alameda County Safe Routes to School | [6 empty] | 2021-10-01 | 2022-09-30 | 1500000 |  |  | 0 | [6 empty] | 0 |  | 1500000 |  | 1500000 | [6 empty] | 1500000 | 1500000 | [5 empty] | 2021-09-30 |  | 1500000
Alameda | AC Transit | ALA210017 | 7250 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6002 |  | -6002() | CON | Tempo Quick Build Transit Lane Delineation | [6 empty] | 2021-10-01 | 2022-09-30 | 300000 |  |  | 0 | [6 empty] | 0 |  | 300000 |  | 300000 | [6 empty] | 300000 | 300000 | [5 empty] | 2021-09-30 |  | 300000
Alameda | AC Transit | ALA210018 | 7251 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6002 |  | -6002() | CON | AC Transit Quick Build Transit Lanes | [6 empty] | 2021-10-01 | 2022-09-30 | 954000 |  |  | 0 | [6 empty] | 0 |  | 954000 |  | 954000 | [6 empty] | 954000 | 954000 | [5 empty] | 2021-09-30 |  | 954000
Alameda | BART | ALA090065 | 4721 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6000 |  | -6000() | CON | BART: Fare Collection Equipment | [6 empty] | 2021-08-27 | 2022-09-30 | 1000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1000000 | 1000000 | 1000000 | [5 empty] | 2021-09-30 |  | 1000000
Alameda | BART | ALA090065 | 4721 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6000 |  | -6000() | CON | BART: Fare Collection Equipment | [6 empty] | 2021-08-27 | 2022-09-30 | 1825000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1825000 | 1825000 | 1825000 | [5 empty] | 2021-09-30 |  | 1825000
Alameda | BART | ALA090065 | 4721 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6000 |  | -6000() | CON | BART: Fare Collection Equipment | [6 empty] | 2021-08-27 | 2022-09-30 | 1510000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1510000 | 1510000 | 1510000 | [5 empty] | 2021-09-30 |  | 1510000
Alameda | Dublin | ALA170062 | 6721 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5432 | 021 | -5432(021) | CON | Dublin Blvd Rehabilitation |  |  |  |  | 2022-04-01 | 2021-05-21 | 2021-12-31 | 2022-01-31 | 661000 |  |  | 0 | [6 empty] | 0 |  | 661000 |  | 661000 | [6 empty] | 661000 | 661000 | [5 empty] | 2021-09-30 |  | 661000
Alameda | Fremont | ALA210014 | 7246 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5322 |  | -5322() | CON | Fremont Blvd/Walnut Ave Protected Intersection |  |  |  |  | 2022-10-01 | 2021-09-30 | 2022-06-30 | 2022-09-30 | 1271000 |  |  | 0 | [6 empty] | 0 |  | 1271000 |  | 1271000 | [6 empty] | 1271000 | 1271000 | [5 empty] | 2021-09-30 |  | 1271000
Alameda | Fremont | ALA210015 | 7247 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5322 |  | -5322() | CON | Fremont Blvd- Grimmer Blvd Protected Intersection |  |  |  |  | 2022-10-01 | 2021-09-30 | 2022-06-30 | 2022-09-30 | 1415000 |  |  | 0 | [6 empty] | 0 |  | 1415000 |  | 1415000 | [6 empty] | 1415000 | 1415000 | [5 empty] | 2021-09-30 |  | 1415000
Alameda | Hayward | ALA170066 | 6737 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5050 | 047 | STPL-5050(047) | CON | Winton Ave Complete Street |  |  | Missed FY20-21 Delivery | Missed FY20-21 Delivery | 2021-12-28 | 2020-06-23 | 2022-02-28 | 2021-01-31 | 1662000 |  |  | 0 | [6 empty] | 0 |  | 1662000 |  | 1662000 | [6 empty] | 1662000 | 1662000 | 9/15/21 - Follow up on Inactive Obligations 8/30/21 - City missed FFY20/21 deadline and must follow-up on Inactives 3/2 - Jacki requested status on 2/26 8/28 - Confirmed for FFY20/21 |  |  |  |  | 2020-09-30 |  | 1662000
Alameda | LAVTA | ALA210016 | 7248 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6193 |  | -6193() | PE | LAVTA Passenger Facilities Enhancements | [6 empty] | 2021-10-01 | 2022-09-30 | 182000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 182000 | 182000 | 182000 | 8/30/21 - LAVTA preparing FTA Transfer |  |  |  |  | 2021-09-30 |  | 182000
Alameda | LAVTA | ALA210016 | 7248 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6193 |  | -6193() | CON | LAVTA Passenger Facilities Enhancements | [6 empty] | 2021-10-01 | 2022-09-30 | 1818000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1818000 | 1818000 | 1818000 | 8/30/21 - LAVTA preparing FTA Transfer |  |  |  |  | 2021-09-30 |  | 1818000
Alameda | MTC | ALA190018 | 6963 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6084 |  | -6084() | CON | Bay Bridge Forward: Alameda I-580 WB HOV Lane Ext | [7 empty] | 2022-09-30 | 7000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 7000000 | 7000000 | 7000000 | [5 empty] | 2021-09-30 |  | 7000000
Alameda | Oakland | ALA170064 | 6726 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5012 | 157 | -5012(157) | CON | Oakland Various Streets Improvements |  |  |  |  | 2022-06-30 | 2019-04-04 | 2022-01-31 | 2022-01-31 | 4895000 |  |  | 0 | [6 empty] | 0 |  | 4895000 |  | 4895000 | [6 empty] | 4895000 | 4895000 | 9/15/21 - Follow up on Inactive Obligations 8/30/21 - City must follow up on Inactives. |  |  |  |  | 2021-09-30 |  | 4895000
Alameda | Oakland | VAR170002 | 6976 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5012 | 159 | HSIPL-5012(159) | ROW | Foothill Blvd & MacArthur Blvd Pedestrian Safety | [5 empty] | 2019-06-14 |  | 2021-12-31 | 37800 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 37800 | [5 empty] | 37800 | 37800 | [5 empty] | 2021-09-30 |  | 37800
Alameda | Oakland | VAR170002 | 6976 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5012 | 159 | HSIPL-5012(159) | CON | Foothill Blvd & MacArthur Blvd Pedestrian Safety |  |  |  |  | 2022-06-30 | 2019-06-14 |  | 2021-12-31 | 869130 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 869130 | [5 empty] | 869130 | 869130 | [5 empty] | 2021-09-30 |  | 869130
Alameda | Oakland | VAR170002 | 6977 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5012 | 158 | HSIPL-5012(158) | CON | Oakland - Various Intersection Imprvmnts H9-04-022 |  |  |  |  | 2022-01-31 | 2019-06-18 |  | 2021-12-31 | 250000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 250000 | [5 empty] | 250000 | 250000 | [5 empty] | 2021-09-30 |  | 250000
Alameda | Oakland | ALA170043 | 6531 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5012 | 154 | ATPL-5012(154) | CON | 14th Street: Safe Routes in the City |  |  |  |  | 2022-08-31 | 2018-06-30 |  | 2022-08-31 | 9343000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 9343000 |  |  | 9343000 | 9343000 | 9/3 - Programmed in FFY22/23 3/2 - CTC approved extension in Oct 2020 8/28 - Project pushed out to FFY 21/22. Waiting for CTC extension approval 3/23 - Ext CON request to 2022 at May CTC meeting. 8/19 - Sponsor will apply for ext by 11/1/19 |  |  |  |  | 2019-10-01 |  | 9343000
Alameda | Oakland | ALA170043 | 6531 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5012 | 154 | -5012(154) | CON | 14th Street: Safe Routes in the City |  |  |  |  | 2022-08-31 | 2018-06-30 |  | 2022-09-30 | 1000000 | [9 empty] | 0 |  |  |  | 0 | [5 empty] | 1000000 | 1000000 | 1000000 | 8/30/21 - Need to Coordinate RFA with ATP allocation June 22. Funds programmed in FFY23 in TIP - move up in TIP or use EPSP? |  |  |  |  | 2021-09-30 |  | 1000000
Alameda | Oakland | VAR170012 | 5221 | 33C0215 | HBP-Seismic | Bridge | STPLZ | 5012 | 124 | STPLZ-5012(124) | CON | Leimert Blvd over Sausal Creek |  |  |  |  | 2022-03-31 | 2017-06-01 | 2021-09-30 | 2021-04-30 | 7500000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 7500000 |  |  |  |  | 7500000 | 7500000 | 3/5 - Executed PDA states RFA CON in April 21 |  |  |  |  | 2021-03-05 |  | 7500000
Alameda | San Leandro | VAR170002 | 7009 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5041 | 049 | HSIPL-5041(049) | CON | Wicks Blvd / Manor Blvd Intersection Improvements |  |  |  |  | 2022-05-31 | 2019-11-08 | 2021-12-31 | 2022-06-30 | 286560 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 286560 | [5 empty] | 286560 | 286560 | [5 empty] | 2021-09-30 |  | 286560
Contra Costa | Brentwood | CC-170034 | 6705 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5300 | 013 | STPL-5300(013) | CON | Brentwood Various Streets and Roads Preservation |  |  |  |  | 2022-05-31 | 2021-01-28 | 2021-12-31 | 2022-01-31 | 628000 |  |  | 0 | [6 empty] | 0 |  | 628000 |  | 628000 | [6 empty] | 628000 | 628000 | [5 empty] | 2021-09-30 |  | 628000
Contra Costa | CCTA |  |  | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6072 |  | -6072() |  | East Bay Integration and Coordination Implementation Planning | [6 empty] | 2022-09-30 | 2022-09-30 | 500000 |  |  | 0 | [6 empty] | 0 |  | 500000 |  | 500000 | [6 empty] | 500000 | 500000 | 8/30/21 - CCTA will work with MTC staff to see if the Study can be funded through FTA and therefore not have to go to DLAE. FTA transfer will be completed before 9/30/22. |  |  |  |  | 2021-09-30 |  | 500000
Contra Costa | Concord | CC-210003 | 7232 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5135 |  | -5135() | CON | East Downtown Concord PDA Access and SR2T |  |  |  |  | 2023-01-01 | 2021-10-01 | 2022-07-31 | 2022-09-30 | 2164000 |  |  | 0 | [6 empty] | 0 |  | 2164000 |  | 2164000 | [6 empty] | 2164000 | 2164000 | [5 empty] | 2021-09-30 |  | 2164000
Contra Costa | Concord | CC-170039 | 6718 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5135 | 059 | CML-5135(059) | CON | Monument Boulevard Class I Path |  |  |  |  | 2022-03-01 | 2020-04-14 | 2021-12-30 | 2022-01-31 | 3715000 |  |  | 0 | [6 empty] | 0 |  |  | 3715000 | 3715000 | [6 empty] | 3715000 | 3715000 | [5 empty] | 2021-09-30 |  | 3715000
Contra Costa | Concord | VAR170002 | 6979 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5135 | 056 | HSIPL-5135(056) | ON | Concord Citywide Traffic System Update (H9-04-008) |  |  |  |  | 2021-12-01 | 2019-07-23 | 2021-09-01 | 2022-06-30 | 2386976 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 2386976 | [5 empty] | 2386976 | 2386976 | [5 empty] | 2021-09-30 |  | 2386976
Contra Costa | Contra Costa County | VAR170002 | 6460 | H8-04-006 | HSIP 8 | HSIP | HSIPL | 5928 | 140 | HSIPL-5928(140) | CON | Danville Blvd/Orchard Ct Comp Streets H8- |  |  | Ext to 12/31/21 | 2021-03-04 | 2022-04-01 | 2017-05-27 | 2021-12-31 | 2021-12-31 | 2233000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 2233000 | [5 empty] | 2233000 | 2233000 | 3/4 - Extension was to 12/31/21 was granted. Request for project update. 9/1 - The County intends to ask for a time extension due to the COVID virus and has discuss with with Caltrans Local Assistance. They requested us to wait and request this extension closer to the obligation deadline, somewhere in the January time period. 8/26 - ROW extended? Requested confirmation from CCTA. |  |  | 19/20 | 19/20 | 2020-09-30 |  | 2233000
Contra Costa | Contra Costa County | VAR170002 | 6462 | H8-04-008 | HSIP 8 | HSIP | HSIPL | 5928 | 143 | HSIPL-5928(143) | CON | Byron Highway/Byer Road Safety |  |  | Ext to 12/31/21 | 2021-03-04 | 2022-04-19 | 2017-06-22 | 2021-11-01 | 2021-12-31 | 508230 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 508230 | [5 empty] | 508230 | 508230 | 3/4 - Extension was to 12/31/21 was granted. Request for project update. 9/1 - The County intends to ask for a time extension due to the COVID virus and has discuss with with Caltrans Local Assistance. They requested us to wait and request this extension closer to the obligation 8/26 - ROW extended? Requested confirmation from CCTA. |  |  | 19/20 | 19/20 | 2020-09-30 |  | 508230
Contra Costa | Contra Costa County | VAR170002 | 6973 | H9-04-010 | HSIP 9 | HSIP | HSIPL | 5928 | 157 | HSIPL-5928(157) | CON | H9-04-010 Crockett Area Guardrail Upgrades |  |  | RFA at CT-HQ | 2021-09-02 | 2021-04-28 | 2019-07-19 | 2021-06-18 | 2021-12-31 | 999963 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 999963 | [5 empty] | 999963 | 999963 | 8/26 - Project will obligated in FFY20/21. Need to change in FMS to 2021 6/6 - Deadline 12/31/21? |  |  |  |  | 2020-09-30 |  | 999963
Contra Costa | Contra Costa County | VAR170012 | 7031 | 28C0442 | HBP-Seismic | Bridge | BRLS | 5928 | 128 | BRLS-5928(128) | CON | Marsh Dr Bridge 28c0442 over WC Channel Replacemnt |  |  |  |  | 2021-04-20 | 2016-06-07 | 2021-02-12 | 2022-09-30 | 13475373 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 13475373 |  |  |  |  | 13475373 | 13475373 | [5 empty] | 2021-09-30 |  | 13475373
Contra Costa | Danville | CC-170058 | 6715 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5434 |  | -5434() | CON | Camino Ramon Improvements |  |  |  |  | 2022-03-30 | 2021-08-26 | 2022-01-31 | 2022-01-31 | 1357000 |  |  | 0 | [6 empty] | 0 |  | 1357000 |  | 1357000 | [6 empty] | 1357000 | 1357000 | 9/15/21 - Follow with City on Inactive Obligation |  |  |  |  | 2021-09-30 |  | 1357000
Contra Costa | Danville | CC-170058 | 6715 | EARMARK-T5-RE | EARMARK | EARMARK |  | 5434 |  | -5434() | CON | Camino Ramon Improvements |  |  |  |  | 2022-03-30 | 2021-08-26 | 2022-01-31 | 2022-01-31 | 111885 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 111885 | 111885 | 111885 | [5 empty] | 2021-09-30 |  | 111885
Contra Costa | Danville | CC-170001 | 6343 | STP-T4-2-OBAG | OBAG | OBAG |  | 5434 |  | -5434() | CON | San Ramon Valley Blvd Slurry Seal and Striping |  |  |  |  | 2022-06-01 | 2021-10-04 | 2022-01-31 | 2022-01-31 | 1475000 |  |  | 0 | [6 empty] | 0 |  | 1475000 |  | 1475000 | [6 empty] | 1475000 | 1475000 | 9/15/21 - Follow with City on Inactive Obligation |  |  |  |  | 2021-09-15 |  | 1475000
Contra Costa | Hercules | CC-170043 | 6734 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5117 | 016 | STPL-5117(016) | CON | Hercules -Sycamore Pavement Rehabilitation |  |  |  |  | 2022-05-11 | 2020-06-12 | 2022-01-31 | 2022-01-31 | 492000 |  |  | 0 | [6 empty] | 0 |  | 492000 |  | 492000 | [6 empty] | 492000 | 492000 | [5 empty] | 2021-09-30 |  | 492000
Contra Costa | Orinda | VAR170012 | 5336 | 28C0331 | HBP-Seismic | Bridge | STPLZ | 5444 | 018 | STPLZ-5444(018) | CON | Bear Creek Road over San Pablo Creek |  |  |  |  | 2022-03-01 | 2018-09-11 |  | 2020-08-01 | 115062 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 115062 |  |  |  |  | 115062 | 115062 | [5 empty] | 2019-10-01 |  | 115062
Contra Costa | Orinda | VAR170012 | 5335 | 28C0330 | HBP-Seismic | Bridge | STPLZ | 5444 | 019 | STPLZ-5444(019) | CON | Miner Road over San Pablo Creek |  |  |  |  | 2022-03-01 | 2018-09-11 |  | 2020-04-01 | 957500 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 957500 |  |  |  |  | 957500 | 957500 | [5 empty] | 2019-10-01 |  | 957500
Contra Costa | Pinole | CC-210009 | 7267 | STP-T5-OBAG2-CO | OBAG 2 | OBAG |  | 5126 |  | -5126() | CON | Safety Improvements at Appian Way and Marlesta Rd. |  |  |  |  | 2022-04-01 | 2021-10-01 | 2022-01-31 | 2022-01-31 | 350000 |  |  | 0 | [6 empty] | 0 |  | 350000 |  | 350000 | [6 empty] | 350000 | 350000 | [5 empty] | 2021-09-15 |  | 350000
Contra Costa | Pittsburg | CC-170042 | 6733 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5127 | 041 | STPL-5127(041) | CON | City of Pittsburg Pavement Improvements |  |  |  |  | 2022-07-01 | 2021-08-03 | 2022-01-31 | 2022-01-31 | 2410000 |  |  | 0 | [6 empty] | 0 |  | 2410000 |  | 2410000 | [6 empty] | 2410000 | 2410000 | [5 empty] | 2021-09-30 |  | 2410000
Contra Costa | Richmond | CC-210007 | 7283 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5137 |  | -5137() | CON | Richmond 13th Street Complete Streets Imps |  |  |  |  | 2021-03-23 | 2021-10-04 | 2022-09-30 | 2022-09-30 | 2821000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 2821000 | 2821000 | 2821000 | [5 empty] | 2021-09-30 |  | 2821000
Contra Costa | San Pablo | CC-170031 | 6679 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5303 |  | -5303() | CON | Giant Road Cycletrack & Pavement Rehabilitation |  |  |  |  | 2023-02-28 | 2021-11-30 | 2022-09-01 | 2022-09-30 | 700000 |  |  | 0 | [6 empty] | 0 |  | 700000 |  | 700000 | [6 empty] | 700000 | 700000 | 9/16/21 - The STP funded the original pavement rehab project. Quick Strick funds programmed for Cycle track. Projects are now combined as one project. |  |  |  |  | 2021-09-30 |  | 700000
Contra Costa | San Pablo | CC-170031 | 6679 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5303 | 022 | STPL-5303(022) | CON | San Pablo - Giant Road Pavement Rehabilitation |  |  |  |  | 2023-02-28 | 2021-11-30 | 2022-09-01 | 2021-01-31 | 618000 |  |  | 0 | [6 empty] | 0 |  | 618000 |  | 618000 | [6 empty] | 618000 | 618000 | 9/16/21 - The STP funded the original pavement rehab project. Quick Strick funds programmed for Cycle track. Projects are now combined as one project. 9/15/21 - Request to add back on AOP. Missed FFY20-21 AOP 8/30/21 - Request to move to FY22/23 Archeological study may prevent obligation til FY21/22 |  |  |  |  | 2020-09-30 |  | 618000
Contra Costa | San Pablo | VAR170002 | 6985 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5303 | 020 | HSIPL-5303(020) | CON | Intersection Church/Willow, El Portal/Mission Bell |  |  | RFA at CT-District | 2021-09-01 | 2022-02-15 | 2019-06-26 | 2021-10-15 | 2022-06-30 | 750870 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 750870 | [5 empty] | 750870 | 750870 | [5 empty] | 2020-08-27 |  | 750870
Marin | GGBHTD | MRN050018 | 1391 | EARMARK-T3-HPP | EARMARK | EARMARK | RPSTPL | 6003 | 010 | RPSTPL-6003(010) | CON | Golden Gate Bridge Seismic Retrofit, Phase 3B | [7 empty] | 2022-01-31 | 1430620.54 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1430620.54 | 1430620.54 | 1430620.54 | 8/18 - GGB will submit a TIP revision In Nov/Dec to move partial funds to MRN050018. |  |  |  |  | 2021-09-30 |  | 1430620.54
Marin | Marin County | VAR170002 | 6264 | HSIP-T5-7 | HSIP 7 | HSIP | HSIPL | 5927 | 115 | HSIPL-5927(115) | CON | HSIP7-04-011 - Arterials & Collector Sign Upgrades |  |  | Ext to 4/1/22 | 2021-09-23 |  |  |  | 2022-04-01 | 445500 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 445500 | [5 empty] | 445500 | 445500 | 9/23/21 - County's petition to ext. obligation deadline to 4/1/22 was approved. 9/3 - County is petitioning an extension request in Spetember 2021 6/24 - Xi is working with HQ on the options for the County. 11/16 - Caltrans granted extension to 6/30/21 |  |  |  |  | 2020-09-23 |  | 445500
Marin | Marin County | VAR170002 | 6968 | H9-04-017 | HSIP 9 | HSIP | HSIPL | 5927 | 123 | HSIPL-5927(123) | CON | Marin Co-Upgrade Non-Standard Guardrails H9-04-017 |  |  |  |  | 2022-06-01 | 2019-06-04 | 2021-01-31 | 2021-12-31 | 861200 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 861200 | [5 empty] | 861200 | 861200 | 9/1 - Project confirmed for FFY20/21. 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 861200
Marin | Marin County | VAR170002 | 6969 | H9-04-016 | HSIP 9 | HSIP | HSIPL | 5927 | 122 | HSIPL-5927(122) | CON-CE | Countywide Signal Upgrade Project (HSIP9-04-016) |  |  |  |  | 2022-06-01 | 2019-05-14 | 2022-06-01 | 2022-06-30 | 2300200 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 2300200 | [5 empty] | 2300200 | 2300200 | Project will obligation FFY21/22 9/1 - Project confirmed for FFY20/21. 6/6 - Deadline 12/31/21? |  |  |  |  | 2020-09-30 |  | 2300200
Marin | MCTD | MRN210002 | 7197 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6343 |  | -6343() | PE | MCTD - Bus Stop Improvements | [7 empty] | 2022-09-30 | 80000 |  |  | 0 | [6 empty] | 0 |  | 80000 |  | 80000 | [6 empty] | 80000 | 80000 | [5 empty] | 2021-09-30 |  | 80000
Marin | MCTD | MRN210002 | 7197 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6343 |  | -6343() | CON | MCTD - Bus Stop Improvements | [7 empty] | 2022-09-30 | 1120000 |  |  | 0 | [6 empty] | 0 |  | 1120000 |  | 1120000 | [6 empty] | 1120000 | 1120000 | [5 empty] | 2021-09-30 |  | 1120000
Marin | Novato | VAR170002 | 7001 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5361 | 031 | HSIPL-5361(031) | CON | Novato Traffic, Bicycle & Pedestrian Improvements |  |  | RFA at CT-HQ | 2021-10-11 |  |  |  | 2022-06-30 | 1146300 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1146300 | [5 empty] | 1146300 | 1146300 | [5 empty] | 2021-09-30 |  | 1146300
Marin | San Rafael | VAR170002 | 6982 | H9-04-030 | HSIP 9 | HSIP | HSIPL | 5043 | 043 | HSIPL-5043(043) | CON | H9-04-030 Third Street Safety Improvements Project |  |  |  |  | 2021-05-17 | 2019-03-22 |  | 2022-06-30 | 1293800 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1293800 | [5 empty] | 1293800 | 1293800 | 6/25 - City plans to submit RFA in September 9/1 - Project confirmed for FFY20/21 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 1293800
Marin | SMART |  | 7294 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6411 |  | -6411() | CON | SMART Rail and Pathway (Phase 2) | [7 empty] | 2022-09-30 | 1858000 |  |  | 0 | [6 empty] | 0 |  | 1858000 |  | 1858000 | [6 empty] | 1858000 | 1858000 | [5 empty] | 2021-09-30 |  | 1858000
Napa | MTC | NAP190007 | 7162 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6084 |  | -6084() | PE | Napa Valley Forward: Safety & Operational Impv | [7 empty] | 2022-09-30 | 1200000 |  |  | 0 | [6 empty] | 0 |  | 1200000 |  | 1200000 | [6 empty] | 1200000 | 1200000 | [5 empty] | 2021-09-30 |  | 1200000
Napa | MTC | NAP190007 | 7162 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6084 |  | -6084() | ROW | Napa Valley Forward: Safety & Operational Impv | [7 empty] | 2022-09-30 | 150000 |  |  | 0 | [6 empty] | 0 |  | 150000 |  | 150000 | [6 empty] | 150000 | 150000 | [5 empty] | 2021-09-30 |  | 150000
Napa | MTC | NAP190007 | 7162 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | Napa Valley Forward: Safety & Operational Impv | [7 empty] | 2022-09-30 | 5650000 |  |  | 0 | [6 empty] | 0 |  | 5650000 |  | 5650000 | [6 empty] | 5650000 | 5650000 | [5 empty] | 2021-09-30 |  | 5650000
Napa | Napa County | VAR170002 | 6999 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5921 | 079 | HSIPL-5921(079) | CON | H9-04-018 Silverado Trail Guardrail Upgrades | [7 empty] | 2021-12-31 | 894100 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 894100 | [5 empty] | 894100 | 894100 | [5 empty] | 2021-09-30 |  | 894100
Napa | Napa County | VAR170002 | 6996 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5921 | 080 | HSIPL-5921(080) | CON | H9-04-019 Silverado Trail Striping | [7 empty] | 2021-12-31 | 1626700 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1626700 | [5 empty] | 1626700 | 1626700 | [5 empty] | 2021-09-30 |  | 1626700
Napa | NVTA | NAP150003 | 6281 | ATP-REG-T4-2-FED | ATP-REG | ATP-FED | ATPL | 6429 |  | ATPL-6429() | CON | Napa Valley Vine Trail - St. Helena to Calistoga | Allocated | 2021-05-13 |  |  | 2021-11-17 | 2019-09-11 | 2022-03-01 | 2021-02-28 | 6106000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 6106000 |  |  | 6106000 | 6106000 | 9/10 - Plan to allocate at March 2021 meeting NVTA will request 20 month extension |  |  |  |  | 2019-10-01 |  | 6106000
Napa | NVTA | NAP150003 | 6281 | STP-T5-OBAG2-REG-PCA | OBAG 2 | STP | ATPL | 6510 | 003 | ATPL-6510(003) | CON | Napa Valley Vine Trail - St. Helena to Calistoga |  |  |  |  | 2021-11-17 | 2019-09-11 | 2022-03-01 | 2021-01-31 | 711000 |  |  | 0 | [6 empty] | 0 |  | 711000 |  | 711000 | [6 empty] | 711000 | 711000 | 9/15/21 - Preparing RFA now and plan to obligate with ATP allocation funds in Mar 2022 9/10 - Plan to allocate at March 2021 meeting |  |  |  |  | 2020-09-30 |  | 711000
Napa | NVTA | NAP170004 | 6599 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6510 |  | -6510() | CON | Napa County Safe Routes to Schools | [7 empty] | 2022-09-30 | 100000 |  |  | 0 | [6 empty] | 0 |  | 100000 |  | 100000 | [6 empty] | 100000 | 100000 | [5 empty] | 2021-09-30 |  | 100000
Napa | Saint Helena | VAR170002 | 6998 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5051 | 005 | HSIPL-5051(005) | CON | Silverado Trail Guardrail Replacement H9-04-032 | [7 empty] | 2022-06-30 | 486100 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 486100 | [5 empty] | 486100 | 486100 | [5 empty] | 2021-09-30 |  | 486100
Region | MTC | REG170016 | 6770 | STP-T5-OBAG2-REG-PDA | OBAG 2 | STP | STPLNI | 6084 | 232 | STPLNI-6084(232) | CON | Regional Planning - PDA Implementation |  |  | RFA at CT-HQ | 2021-09-06 |  |  |  | 2022-01-31 | 8950000 |  |  | 0 | [6 empty] | 0 |  | 8950000 |  | 8950000 | [6 empty] | 8950000 | 8950000 | [5 empty] | 2021-09-30 |  | 8950000
Region | MTC | VAR170024 | 6576 | STP-T4-1-CCI | OBAG | STP |  | 6084 |  | -6084() | CON | Bike Share Capital Program | [7 empty] | 2022-01-31 | 700000 |  |  | 0 | [6 empty] | 0 |  | 700000 |  | 700000 | [6 empty] | 700000 | 700000 | [5 empty] | 2021-09-30 |  | 700000
Region | MTC | Various |  | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 6084 | 206 | STPL-6084(206) | OTHER | Regional Planning Activities and PPM |  |  | RFA at FHWA | 2021-10-08 |  |  |  | 2022-09-30 | 3086000 |  |  | 0 | [6 empty] | 0 |  | 3086000 |  | 3086000 | [6 empty] | 3086000 | 3086000 | [5 empty] | 2021-06-28 |  | 3086000
San Francisco | BART | SF-170016 | 6727 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6000 |  | -6000() | CON | Embarcadero Stn: New North-Side Platform Elevator | [7 empty] | 2022-09-30 | 3144302 |  |  | 0 | [6 empty] | 0 |  | 3144302 |  | 3144302 | [6 empty] | 3144302 | 3144302 | [5 empty] | 2021-09-30 |  | 3144302
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0006 | HBP-Seismic | Bridge | STPLZ | 6272 | 029 | STPLZ-6272(029) | CON | Hillcrest Road West of Yerba Buena Island | [7 empty] | 2022-09-30 | 2042843.2572 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 2042843.2572 |  |  |  |  | 2042843.2572 | 2042843.2572 | [5 empty] | 2021-09-30 |  | 2042843.2572
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0002 | HBP-Seismic | Bridge | STPLZ | 6272 | 026 | STPLZ-6272(026) | ROW | WB I-80 on ramp West of Yerba Buena Island | [7 empty] | 2022-09-30 | 550000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 550000 |  |  |  |  | 550000 | 550000 | [5 empty] | 2021-09-30 |  | 550000
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0002 | HBP-Seismic | Bridge | STPLZ | 6272 | 026 | STPLZ-6272(026) | CON | WB I-80 on ramp West of Yerba Buena Island | [7 empty] | 2022-09-30 | 19077010.9303 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 19077010.9303 |  |  |  |  | 19077010.9303 | 19077010.9303 | [5 empty] | 2021-09-30 |  | 19077010.9303
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0003 | HBP-Seismic | Bridge | STPLZ | 6272 | 027 | STPLZ-6272(027) | ROW | EB I-80 off ramp to TI Road (2 Bridges) | [7 empty] | 2022-09-30 | 300000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 300000 |  |  |  |  | 300000 | 300000 | [5 empty] | 2021-09-30 |  | 300000
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0003 | HBP-Seismic | Bridge | STPLZ | 6272 | 027 | STPLZ-6272(027) | CON | EB I-80 off ramp to TI Road (2 Bridges) | [7 empty] | 2022-09-30 | 8460249.4289 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 8460249.4289 |  |  |  |  | 8460249.4289 | 8460249.4289 | [5 empty] | 2021-09-30 |  | 8460249.4289
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0004 | HBP-Seismic | Bridge | STPLZ | 6272 | 028 | STPLZ-6272(028) | CON | Treasure Island Road West of SFOBB | [7 empty] | 2022-09-30 | 1724961.1255 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 1724961.1255 |  |  |  |  | 1724961.1255 | 1724961.1255 | [5 empty] | 2021-09-30 |  | 1724961.1255
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0008 | HBP-Seismic | Bridge | STPLZ | 6272 | 032 | STPLZ-6272(032) | CON | Treasure Island road West of SFOBB | [7 empty] | 2022-09-30 | 505169.0061 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 505169.0061 |  |  |  |  | 505169.0061 | 505169.0061 | [5 empty] | 2021-09-30 |  | 505169.0061
San Francisco | SFCTA | SF-070027 | 3741 | 01CA007A | HBP-Seismic | Bridge | STPLZ | 6272 | 030 | STPLZ-6272(030) | CON | Treasure Island Road West of SFOBB | [7 empty] | 2022-09-30 | 271062.3426 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 271062.3426 |  |  |  |  | 271062.3426 | 271062.3426 | [5 empty] | 2021-09-30 |  | 271062.3426
San Francisco | SFCTA | SF-070027 | 3741 | 01CA007B | HBP-Seismic | Bridge | STPLZ | 6272 | 031 | STPLZ-6272(031) | CON | Treasure Isand Road west of SFOBB | [7 empty] | 2022-09-30 | 357315.4159 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 357315.4159 |  |  |  |  | 357315.4159 | 357315.4159 | [5 empty] | 2021-09-30 |  | 357315.4159
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0001 | HBP-Seismic | Bridge | STPLZ | 6272 | 024 | STPLZ-6272(024) | CON | WB SFOBB on ramp West of YBI | [7 empty] | 2022-09-30 | 369633.9756 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 369633.9756 |  |  |  |  | 369633.9756 | 369633.9756 | [5 empty] | 2021-09-30 |  | 369633.9756
San Francisco | SFMTA | SF-210003 | 7212 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6328 |  | -6328() | CON | San Francisco - Folsom Streetscape | [7 empty] | 2022-09-30 | 5000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 5000000 | 5000000 | 5000000 | 8/31/21 - anticipated to be reprogrammed to the SFCTA’s Yerba Buena Island (YBI) West Side Bridges Project once $5,000,000 in ATP Augmentation funding is approved for the Folsom project in the fall. Per Aprile’s conversation with John on August 26, we understand that the CRRSAA funds for Folsom will automatically be included in the upcoming Annual Obligation Plan as it is programmed in the TIP and must be obligated by September 30, 2022. Once the anticipated ATP Augmentation and funding exchange is approved, we will notify John so that the Annual Obligation Plan and the TIP can be updated. |  |  |  |  | 2021-09-30 |  | 5000000
San Mateo | Belmont | SM-170043 | 6667 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5268 | 022 | -5268(022) | CON | Belmont Pavement Preservation |  |  |  |  | 2022-04-01 | 2020-08-28 | 2021-12-31 | 2022-01-31 | 467000 |  |  | 0 | [6 empty] | 0 |  | 467000 |  | 467000 | [6 empty] | 467000 | 467000 | 9/15/21 - Sounds like the initial invoice was sent via US mail and didn’t make it to the Local Assistance group at District 4. The material was resubmitted via email on 9/10/21. Hoping to see it as under review in the next update of the “inactive” list. 9/15/21 - Request for Inactive Obligation update. Will hire new SPOC on 9/20/21. |  |  |  |  | 2021-09-30 |  | 467000
San Mateo | Burlingame |  | 7292 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5171 |  | -5171() | CON | City-Wide Ped Safe Routes and Mobility Improvement |  |  |  |  | 2022-11-01 | 2022-04-01 | 2022-09-01 | 2022-09-30 | 200000 |  |  | 0 | [6 empty] | 0 |  | 200000 |  | 200000 | [6 empty] | 200000 | 200000 | 8/31/21 - Will be included in TIP after conformity grace period. |  |  |  |  | 2021-09-30 |  | 200000
San Mateo | Redwood City | SM-210002 | 7235 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5029 |  | -5029() | CON | Roosevelt Ave Quick-build Traffic Calming |  |  |  |  | 2022-08-01 | 2021-09-30 | 2022-03-30 | 2022-09-30 | 755000 |  |  | 0 | [6 empty] | 0 |  | 755000 |  | 755000 | [6 empty] | 755000 | 755000 | [5 empty] | 2021-09-30 |  | 755000
San Mateo | San Mateo Co | SM-210005 | 7276 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 5935 | 087 | STPL-5935(087) | PE | Broadmoor Safe Routes to School Ped Impvts |  |  | RFA at CT-HQ | 2021-10-08 |  | 2021-09-15 | 2021-10-16 | 2022-09-30 | 210000 |  |  | 0 | [6 empty] | 0 |  | 210000 |  | 210000 | [6 empty] | 210000 | 210000 | [5 empty] | 2021-09-30 |  | 210000
San Mateo | San Mateo Co | SM-210005 | 7276 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5935 |  | -5935() | CON | Broadmoor Safe Routes to School Ped Impvts |  |  |  |  | 2022-11-15 | 2021-09-15 | 2022-09-01 | 2022-09-30 | 1209000 |  |  | 0 | [6 empty] | 0 |  | 1209000 |  | 1209000 | [6 empty] | 1209000 | 1209000 | [5 empty] | 2021-09-30 |  | 1209000
San Mateo | SMCCAG | SM-070002 | 2561 | RIP-T4-12-FED-SM | RTIP | RTIP-FED |  | 6419 |  | -6419() | CON | San Mateo Countywide ITS Improvements | Allocated | 2021-01-28 |  |  | 2021-06-15 | 2018-05-16 |  | 2020-01-31 | 2044000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 2044000 |  |  |  | 2044000 | 2044000 | [5 empty] | 2020-08-31 |  | 2044000
San Mateo | SMCCAG | SM-090014 | 4253 | RIP-T4-14-FED-SM | RTIP | RTIP-FED |  | 6419 |  | -6419() | PSE | Improve US 101 operations near Rte 92 | [7 empty] | 2022-06-30 | 3217000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 3217000 |  |  |  | 3217000 | 3217000 | 8/31/21 - STIP PSE Phase Assume March 2022 CTC allocation |  |  |  |  | 2021-09-30 |  | 3217000
San Mateo | South San Francisco | VAR170002 | 6991 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5177 | 043 | HSIPL-5177(043) | CON | Ped. Imp. On W. Orange and Hillsdale (H9-04-031) |  |  | RFA at CT-HQ | 2021-10-08 | 2021-03-15 | 2019-08-07 |  | 2022-06-30 | 204800 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 204800 | [5 empty] | 204800 | 204800 | [5 empty] | 2020-08-31 |  | 204800
San Mateo | South San Francisco | SM-170016 | 6663 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5177 | 040 | -5177(040) | CON | SSF Grand Boulevard Complete Streets (Phase III) |  |  |  |  | 2022-05-01 | 2018-08-24 | 2022-05-01 | 2022-01-31 | 875000 |  |  | 0 | [6 empty] | 0 |  |  | 875000 | 875000 | [6 empty] | 875000 | 875000 | [5 empty] | 2021-09-30 |  | 875000
San Mateo | South San Francisco | SM-170016 | 6663 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5177 | 040 | -5177(040) | CON | SSF Grand Boulevard Complete Streets (Phase III) |  |  |  |  | 2022-05-01 | 2018-08-24 | 2022-05-01 | 2022-09-30 | 2120000 |  |  | 0 | [6 empty] | 0 |  | 2120000 |  | 2120000 | [6 empty] | 2120000 | 2120000 | [5 empty] | 2021-09-30 |  | 2120000
San Mateo | South San Francisco |  | 6663 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5177 |  | -5177() | PE | East of 101 Transit Expansion Project |  |  |  |  | 2022-01-01 | 2022-03-01 | 2022-09-01 | 2022-09-30 | 49924 |  |  | 0 | [6 empty] | 0 |  | 49924 |  | 49924 | [6 empty] | 49924 | 49924 | 8/31/21 - QSTRIKE – Will not be included in TIP until after conformity issue resolved -PEE Phase -City will move PE $ to CON Phase |  |  |  |  | 2021-09-30 |  | 49924
San Mateo | South San Francisco |  | 6663 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5177 |  | -5177() | CON | East of 101 Transit Expansion Project |  |  |  |  | 2022-01-01 | 2022-03-01 | 2022-09-01 | 2022-09-30 | 430076 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 430076 | 430076 | 430076 | 8/31/21 - QSTRIKE -Will not be included in TIP until after conformity issue resolved CON Phase |  |  |  |  | 2021-09-30 |  | 430076
San Mateo | San Bruno | SM-210003 | 7244 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5226 |  | -5226() | CON | San Bruno Transit Corridor Ped Connection Ph4 |  |  |  |  | 2022-01-15 |  | 2022-09-01 | 2022-09-30 | 385000 |  |  | 0 | [6 empty] | 0 |  | 385000 |  | 385000 | [6 empty] | 385000 | 385000 | [5 empty] | 2021-09-30 |  | 385000
San Mateo | San Mateo | SM-170040 | 6643 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5102 | 051 | -5102(051) | CON | San Mateo Street Rehabilitation |  |  |  |  | 2022-07-01 | 2020-07-20 | 2022-01-31 | 2022-01-31 | 1593000 |  |  | 0 | [6 empty] | 0 |  | 1593000 |  | 1593000 | [6 empty] | 1593000 | 1593000 | [5 empty] | 2021-09-30 |  | 1593000
Santa Clara | Campbell | SCL190042 | 6967 | CMAQ-T4-2-OBAG | OBAG | CMAQ | CML | 5306 | 032 | CML-5306(032) | CON | Harriet Avenue Sidewalk Improvements |  |  |  |  | 2022-07-01 | 2021-05-25 | 2021-11-01 | 2022-01-31 | 552672 |  |  | 0 | [6 empty] | 0 |  |  | 552672 | 552672 | [6 empty] | 552672 | 552672 | [5 empty] | 2021-09-30 |  | 552672
Santa Clara | Campbell | SCL190042 | 6967 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5306 | 032 | CML-5306(032) | CON | Harriet Avenue Sidewalk Improvements |  |  |  |  | 2022-07-01 | 2021-05-25 | 2021-11-01 | 2022-01-31 | 447328 |  |  | 0 | [6 empty] | 0 |  |  | 447328 | 447328 | [6 empty] | 447328 | 447328 | [5 empty] | 2021-09-30 |  | 447328
Santa Clara | Cupertino | SCL190036 | 7087 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5318 | 033 | CML-5318(033) | CON | McClellan Road Separated Bikeways (Phase 3) |  |  |  |  | 2022-06-30 | 2021-09-21 | 2022-02-11 | 2022-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  |  | 1000000 | 1000000 | [6 empty] | 1000000 | 1000000 | [5 empty] | 2021-09-30 |  | 1000000
Santa Clara | Cupertino | VAR170002 | 6970 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5318 | 030 | HSIPL-5318(030) | CON | Homestead/ De Anza TS Safety Improvement H9-04-011 | [6 empty] | 2021-12-31 | 2022-06-30 | 182300 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 182300 | [5 empty] | 182300 | 182300 | [5 empty] | 2021-09-30 |  | 182300
Santa Clara | Los Gatos | SCL190033 | 7067 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5067 |  | -5067() | CON | Shannon Road Complete Streets |  |  |  |  | 2022-05-01 | 2021-07-29 |  | 2022-01-31 | 940100 |  |  | 0 | [6 empty] | 0 |  |  | 940100 | 940100 | [6 empty] | 940100 | 940100 | [5 empty] | 2021-09-30 |  | 940100
Santa Clara | Morgan Hill | SCL170063 | 6701 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5152 | 022 | STPL-5152(022) | CON | Dunne Avenue Pavement Rehabilitation |  |  |  |  | 2022-02-16 | 2021-07-12 |  | 2022-01-31 | 857000 |  |  | 0 | [6 empty] | 0 |  | 857000 |  | 857000 | [6 empty] | 857000 | 857000 | [5 empty] | 2021-09-30 |  | 857000
Santa Clara | Mountain View | SCL210012 | 7224 | STP-CRRSAA | OBAG 2 | CRRSAA+ | STPL | 5124 | 037 | STPL-5124(037) | CON | Mountain View - Stierlin Rd Bike-Ped Improvements |  |  |  |  | 2022-06-01 | 2021-09-02 |  | 2022-09-30 | 1486000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1486000 | 1486000 | 1486000 | [5 empty] | 2021-09-30 |  | 1486000
Santa Clara | Mountain View | SCL210012 | 7224 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 5124 | 037 | STPL-5124(037) | CON | Mountain View - Stierlin Rd Bike-Ped Improvements |  |  |  |  | 2022-06-01 | 2021-09-02 |  | 2022-09-30 | 2521000 |  |  | 0 | [6 empty] | 0 |  | 2521000 |  | 2521000 | [6 empty] | 2521000 | 2521000 | [5 empty] | 2021-09-30 |  | 2521000
Santa Clara | MTC | SCL210022 | 7287 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6084 |  | -6084() | OTHER | Diridon Station Planning & Studies | [7 empty] | 2022-09-30 | 1000000 |  |  | 0 | [6 empty] | 0 |  | 1000000 |  | 1000000 | [6 empty] | 1000000 | 1000000 | [5 empty] | 2021-09-30 |  | 1000000
Santa Clara | San Jose | SCL050083 | 1949 | ATP-REG-T4-1-FED | ATP-REG | ATP-FED | ATPL | 5005 | 146 | ATPL-5005(146) | CON | Coyote Creek Trail: Mabury to Empire |  |  |  |  | 2022-06-30 | 2016-11-01 | 2022-03-31 | 2022-03-31 | 4046000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 4046000 |  |  | 4046000 | 4046000 | 6/26 - Will allocate by deadline Working with CTC and Karl on extension. |  |  |  |  | 2019-10-01 |  | 4046000
Santa Clara | San Jose | SCL170031 | 6657 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5005 | 156 | CML-5005(156) | CON | Mt Pleasant Ped & Bike Traffic Safety Improvements |  |  |  |  | 2022-07-01 | 2018-09-14 | 2021-12-31 | 2022-01-31 | 831793 |  |  | 0 | [6 empty] | 0 |  |  | 831793 | 831793 | [6 empty] | 831793 | 831793 | [5 empty] | 2021-09-30 |  | 831793
Santa Clara | San Jose | SCL210013 | 7239 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5005 |  | -5005() | CON | McKee-Julian Quick Strike Improvements |  |  |  |  | spring 2023 | 2022-01-30 | 2022-09-15 | 2022-09-30 | 705000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 705000 | 705000 | 705000 | [5 empty] | 2021-09-30 |  | 705000
Santa Clara | San Jose | SCL210014 | 7240 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5005 |  | -5005() | CON | Bascom Avenue - Quick Strike Improvements |  |  |  |  | spring 2023 | 2022-01-30 | 2022-09-15 | 2022-09-30 | 690000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 690000 | 690000 | 690000 | [5 empty] | 2021-09-30 |  | 690000
Santa Clara | San Jose | SCL210015 | 7241 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5005 |  | -5005() | CON | En Movimiento - Quick Strike Improvements |  |  |  |  | spring 2023 | 2022-01-30 | 2022-09-15 | 2022-09-30 | 1325000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1325000 | 1325000 | 1325000 | [5 empty] | 2021-09-30 |  | 1325000
Santa Clara | San Jose | SCL210016 | 7242 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5005 |  | -5005() | CON | San Jose Downtown Bikeways - Quick Strike |  |  |  |  | spring 2023 | 2022-01-30 | 2022-09-15 | 2022-09-30 | 4025000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 4025000 | 4025000 | 4025000 | [5 empty] | 2021-09-30 |  | 4025000
Santa Clara | San Jose | SCL170061 | 6752 | RIP-T5-18-FED-SCL | RTIP | RTIP-FED | CML | 5005 | 162 | CML-5005(162) | CON | W San Carlos Urban Village Streets Improvements | [7 empty] | 2022-06-30 | 4350000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 4350000 |  |  |  | 4350000 | 4350000 | 9/3 - Will require CTC extrension approval in spring 2022 8/6 - Will not deliver in FY22. Push out to FY23. |  |  |  |  | 2021-09-30 |  | 4350000
Santa Clara | San Jose | SCL170030 | 6648 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5005 | 154 | STPL-5005(154) | CON | McKee Road Safety Improvements |  |  |  |  | 2021-06-30 | 2020-08-10 | 2021-09-30 | 2021-01-31 | 6994933 |  |  | 0 | [6 empty] | 0 |  | 6994933 |  | 6994933 | [6 empty] | 6994933 | 6994933 | 8/31/21 - We are working through one of the draft NTOs for PG&E (which is the last of the 9 NTOs). I have also requested and waiting for confirmation about the most current versions of the Report of Investigation for the city-own utility documents 6/26 - Will obligate FFY20/21 - FR on 8/10/18 |  |  |  |  | 2020-09-30 |  | 6994933
Santa Clara | San Jose | SCL050082 | 1948 | EARMARK-T3-HPP | EARMARK | EARMARK | HPLUL | 5005 | 086 | HPLUL-5005(086) |  | Bay Trail Reach 9 & 9B |  |  | RFA at FHWA | 2021-10-04 | Estimated Summer 2024 | 2007-04-24 | 2021-09-30 | 2021-09-30 | 0 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [6 empty] | 0 | 0 | [5 empty] | 2021-07-01 |  | 0
Santa Clara | San Jose | VAR170002 | 6994 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5005 | 165 | HSIPL-5005(165) | CON | H9-04-027 Monterey Road - HSIP Guardrail Upgrade | [5 empty] | 2021-07-26 | 2021-12-15 | 2021-12-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1000000 | [5 empty] | 1000000 | 1000000 | [5 empty] | 2021-09-30 |  | 1000000
Santa Clara | Santa Clara | SCL170056 | 6669 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5019 | 036 | CML-5019(036) | CON | Santa Clara School Access Improvements |  |  |  |  | 2022-02-28 | 2021-05-13 | 2021-10-31 | 2022-01-31 | 1146000 |  |  | 0 | [6 empty] | 0 |  |  | 1146000 | 1146000 | [6 empty] | 1146000 | 1146000 | [5 empty] | 2021-09-30 |  | 1146000
Santa Clara | Saratoga | SCL170054 | 6664 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5332 |  | -5332() | CON | Saratoga Village Crosswalks and Sidewalk Rehab |  |  |  |  | 2022-06-01 | 2021-10-12 |  | 2022-01-31 | 338000 |  |  | 0 | [6 empty] | 0 |  | 338000 |  | 338000 | [6 empty] | 338000 | 338000 | 9/15 - City to submit FR request and docs to CT this week. 9/15/21 - Request for FR info. |  |  |  |  | 2021-09-30 |  | 338000
Santa Clara | Saratoga | SCL210018 | 7274 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5332 |  | -5332() | CON | Blue Hills Elementary Pedestrian Crossing at UPRR |  |  |  |  | 2022-11-01 |  |  | 2022-09-30 | 1800000 |  |  | 0 | [6 empty] | 0 |  | 1800000 |  | 1800000 | [6 empty] | 1800000 | 1800000 | 8/18 - City requested to move funds to FFY22/23 |  |  |  |  | 2021-09-30 |  | 1800000
Santa Clara | Sunnyvale | SCL170059 | 6829 | ATP-ST-T5-3-ST | ATP-ST | ATP-ST | ATPL | 5213 |  | ATPL-5213() | PSE | Sunnyvale Safe Routes to School Imps | Allocated | 2020-05-13 | CTC Ext Approved | 2019-05-15 | 2021-10-21 | 2020-02-26 |  | 2020-01-31 | 318000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 318000 |  |  | 318000 | 318000 | 8/27 - Was extension approved? 3/23 -Requesting CON extension to FY22 at May meeting |  |  |  |  | 2019-10-01 |  | 318000
Santa Clara | Sunnyvale | SCL170059 | 6829 | ATP-ST-T5-3-ST | ATP-ST | ATP-ST | ATPL | 5213 |  | ATPL-5213() | CON | Sunnyvale Safe Routes to School Imps |  |  | CTC Ext Approved |  | 2022-10-25 | 2020-02-26 | 2022-06-30 | 2022-06-30 | 1509000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 1509000 |  |  | 1509000 | 1509000 | 8/27 - Moved to FY2022? 3/23 -Requesting CON extension to FY22 at May meeting |  |  |  |  | 2019-10-01 |  | 1509000
Santa Clara | Sunnyvale | SCL170017 | 6555 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5213 | 068 | ATPL-5213(068) | PSE | Sunnyvale SNAIL Neighborhood Improvements |  |  | CTC Scope Changed approved |  | 2021-10-29 | 2021-11-30 | 2022-06-30 | 2022-06-30 | 780000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 780000 |  |  | 780000 | 780000 | 8/27 - Construction funding deferred to FY2023 3/23 - Requesting Extension to FY21 at May meeting |  |  |  |  | 2019-10-01 |  | 780000
Santa Clara | Sunnyvale | VAR170002 | 7002 | H9-04-034 | HSIP 9 | HSIP | HSIPL | 5213 | 071 | HSIPL-5213(071) | CON | H9-04-034 Advanced Dilemma Zone Detection Phase 2 |  |  |  |  | 2022-03-01 | 2020-12-14 | 2022-01-31 | 2022-06-30 | 1112000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1112000 | [5 empty] | 1112000 | 1112000 | 8/27 - Execution of construction contract underway. 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 1112000
Santa Clara | Sunnyvale | SCL170027 | 6632 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5213 | 063 | STPL-5213(063) | CON | Sunnyvale Traffic Signal Upgrades/Replacements |  |  | RFA at CT-HQ | 2021-10-08 | 2021-01-25 | 2019-11-01 | 2021-09-30 | 2021-01-31 | 2366000 |  |  | 0 | [6 empty] | 0 |  | 2366000 |  | 2366000 | [6 empty] | 2366000 | 2366000 | 8/31 - City states RFA was submitted on 8/20 8/23 - City received ROW Cert and should submit a RFA in a week or two. |  |  |  |  | 2020-09-30 |  | 2366000
Santa Clara | Sunnyvale |  | 7300 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5213 |  | -5213() | CON | Sunnyvale Bicycle, Pedestrian and SRTS Safety Imps |  |  |  |  | 2022-05-31 |  | 2022-01-30 | 2022-09-30 | 1900000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1900000 | 1900000 | 1900000 | [5 empty] | 2021-09-30 |  | 1900000
Santa Clara | Sunnyvale | SCL170022 | 6566 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5213 |  | -5213() | CON | Java Dr Road Diet and Bike Lanes |  |  |  |  | 2022-06-30 | 2021-08-27 | 2022-01-30 | 2022-01-31 | 128788 |  |  | 0 | [6 empty] | 0 |  |  | 128788 | 128788 | [6 empty] | 128788 | 128788 | [5 empty] | 2021-09-30 |  | 128788
Santa Clara | Sunnyvale | SCL170022 | 6566 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5213 |  | -5213() | PE | Java Dr Road Diet and Bike Lanes | [5 empty] | 2021-08-27 |  | 2021-09-30 | 157212 |  |  | 0 | [6 empty] | 0 |  |  | 157212 | 157212 | [6 empty] | 157212 | 157212 | 9/3 - City is working on Inactive Obligations and would like to remove PE funds to CON. Requested to move unobligated PE funding into Construction |  |  |  |  | 2020-09-30 |  | 157212
Santa Clara | Sunnyvale | SCL170024 | 6617 | CMAQ-T4-2-RSRTS-REG | OBAG | CMAQ |  | 5213 |  | -5213() | CON | East Sunnyvale Area "Sense of Place" |  |  |  |  | 2022-05-03 | 2018-06-05 | 2022-01-30 | 2022-01-31 | 40000 |  |  | 0 | [6 empty] | 0 |  |  | 40000 | 40000 | [6 empty] | 40000 | 40000 | [5 empty] | 2021-09-30 |  | 40000
Santa Clara | Sunnyvale | SCL170024 | 6617 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5213 |  | -5213() | CON | East Sunnyvale Area "Sense of Place" |  |  |  |  | 2022-05-03 | 2018-06-05 | 2022-01-30 | 2022-01-31 | 1701000 |  |  | 0 | [6 empty] | 0 |  |  | 1701000 | 1701000 | [6 empty] | 1701000 | 1701000 | [5 empty] | 2021-09-30 |  | 1701000
Santa Clara | Sunnyvale | SCL170026 | 6627 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5213 |  | -5213() | CON | Lawrence Station Area Sidewalks & Bike Facilities |  |  | NEPA Approved |  | 2022-03-29 | 2021-03-11 | 2022-01-30 | 2022-01-31 | 286000 |  |  | 0 | [6 empty] | 0 |  |  | 286000 | 286000 | [6 empty] | 286000 | 286000 | [5 empty] | 2021-09-30 |  | 286000
Santa Clara | Sunnyvale | SCL170057 | 6764 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ |  | 5213 |  | -5213() | CON | Sunnyvale Ped and Bike Infrastructure Improvements |  |  | NEPA Approved |  | 2022-05-03 | 2021-07-27 | 2022-01-30 | 2022-01-31 | 919000 |  |  | 0 | [6 empty] | 0 |  |  | 919000 | 919000 | [6 empty] | 919000 | 919000 | [5 empty] | 2021-09-30 |  | 919000
Santa Clara | VTA | SCL210017 | 7245 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6264 |  | -6264() | CON | VTA Electronic Locker Upgrade and Replacement | [7 empty] | 2022-09-30 | 1987000 |  |  | 0 | [6 empty] | 0 |  | 1987000 |  | 1987000 | [6 empty] | 1987000 | 1987000 | [5 empty] | 2021-09-30 |  | 1987000
Santa Clara | VTA | SCL150001 | 6045 | RIP-T4-14-FED-SCL | RTIP | RTIP-FED | RPSTPL | 6264 |  | RPSTPL-6264() | PSE | I-680 Soundwalls - Capitol Expwy to Mueller Ave | Allocated | 2019-01-31 | CTC Ext Approved | 2018-06-28 |  |  | 2018-01-31 | 2018-01-31 | 731000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 731000 |  |  |  | 731000 | 731000 | 9/1/21 - Expecting to finsih project by late 2021 8/4 - is ongoing. Expecting to finish by early 2021 |  |  |  |  | 2019-10-01 |  | 731000
Santa Clara | VTA | SCL150001 | 6045 | RIP-T4-14-FED-SCL | RTIP | RTIP-FED |  | 6264 |  | -6264() | CON | I-680 Soundwalls - Capitol Expwy to Mueller Ave | [7 empty] | 2022-06-30 | 3275000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 3275000 |  |  |  | 3275000 | 3275000 | 9/1/21 - Funding allocation extension approved by CTC for 12 months for FY 22. 8/4 - scheduled to be obligated by 6/30/2021. |  |  |  |  | 2020-09-30 |  | 3275000
Santa Clara | VTA | SCL110002 | 4198 | RIP-T5-20-ST-SCL | RTIP | RTIP-ST |  | 6264 |  | -6264() | ROW | Silicon Valley Express Lanes Program - Phase 5 Civil | [7 empty] | 2022-06-30 | 4754000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 4754000 |  |  |  | 4754000 | 4754000 | 9/21 - State Funds, remove from AOP 8/4 - programmed for FY20/21 but has not been allocated |  |  |  |  | 2020-09-30 |  | 4754000
Solano | Benicia | SOL170011 | 6676 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5003 | 031 | CML-5003(031) | CON | Benicia - Park Road Improvements |  |  |  |  | 2022-03-01 | 2018-03-15 |  | 2022-01-31 | 2000000 |  |  | 0 | [6 empty] | 0 |  |  | 2000000 | 2000000 | [6 empty] | 2000000 | 2000000 | [5 empty] | 2021-09-30 |  | 2000000
Solano | Benicia | SOL170011 | 6676 | STP-T5-OBAG2-CO | OBAG 2 | STP | CML | 5003 | 031 | CML-5003(031) | CON | Benicia - Park Road Improvements |  |  |  |  | 2022-03-01 | 2018-03-15 |  | 2022-01-31 | 731000 |  |  | 0 | [6 empty] | 0 |  | 731000 |  | 731000 | [6 empty] | 731000 | 731000 | [5 empty] | 2021-09-30 |  | 731000
Solano | Benicia | VAR170002 | 7005 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5003 | 032 | HSIPL-5003(032) | CON | Benicia: H9-04-005 Guardrail Upgrades |  |  |  |  | 2022-03-01 | 2019-05-30 |  | 2022-06-30 | 861000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 861000 | [5 empty] | 861000 | 861000 | [5 empty] | 2021-09-30 |  | 861000
Solano | Benicia | VAR170002 | 7006 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5003 | 033 | HSIPL-5003(033) | CON | Benicia H9-04-006 Pedestrian Crossing Enhancements |  |  |  |  | 2022-03-01 | 2019-05-03 |  | 2022-06-30 | 222000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 222000 | [5 empty] | 222000 | 222000 | [5 empty] | 2021-09-30 |  | 222000
Solano | Caltrans | SOL110001 | 4801 | RIP-COVID21-SOL | RTIP | RTIP-FED |  |  |  | -() | CON | Solano I-80 Managed Lanes | Allocated | 2021-08-19 | [5 empty] | 2022-06-30 | 1859490 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 1859490 |  |  |  | 1859490 | 1859490 | [5 empty] | 2021-09-30 |  | 1859490
Solano | Fairfield | SOL170010 | 6773 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5132 | 049 | CML-5132(049) | CON | Grange Middle School SR2S and PavementPreservation |  |  |  |  | 2022-06-01 | 2020-04-23 | 2021-11-01 | 2022-01-31 | 260000 |  |  | 0 | [6 empty] | 0 |  |  | 260000 | 260000 | [6 empty] | 260000 | 260000 | [5 empty] | 2021-09-30 |  | 260000
Solano | Fairfield | SOL170010 | 6773 | STP-T5-OBAG2-REG-HIP | OBAG 2 | STP | CML | 5132 | 049 | CML-5132(049) | CON | Grange Middle School SR2S and PavementPreservation |  |  |  |  | 2022-06-01 | 2020-04-23 | 2021-11-01 | 2022-01-31 | 2100000 |  |  | 0 | [6 empty] | 0 |  | 2100000 |  | 2100000 | [6 empty] | 2100000 | 2100000 | [5 empty] | 2021-09-30 |  | 2100000
Solano | Fairfield |  |  | STP-T5-OBAG2-REG-SSM | OBAG2 | STP |  | 5132 |  | -5132() |  | Fairfield/Vacaville Hannigan Station Capacity Improvements | [7 empty] | 2022-09-30 | 1900000 |  |  | 0 | [6 empty] | 0 |  | 1900000 |  | 1900000 | [6 empty] | 1900000 | 1900000 | [5 empty] | 2021-09-30 |  | 1900000
Solano | Fairfield | VAR170002 | 7007 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5132 |  | HSIPL-5132() | CON | Fairfield: H9-04-013 Guardrail Project | [7 empty] | 2022-06-30 | 655400 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 655400 | [5 empty] | 655400 | 655400 | [5 empty] | 2021-09-30 |  | 655400
Solano | Fairfield | VAR170002 | 7010 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5132 |  | HSIPL-5132() | CON | Fairfield Signalized Intersection Improvements | [7 empty] | 2022-06-30 | 935150 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 935150 | [5 empty] | 935150 | 935150 | [5 empty] | 2021-09-30 |  | 935150
Solano | Fairfield | VAR170002 | 7011 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5132 |  | HSIPL-5132() | CON | Fairfield: HSIP 9 HAWK Installation H9-04-014 | [7 empty] | 2022-06-30 | 1226771 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1226771 | [5 empty] | 1226771 | 1226771 | [5 empty] | 2021-09-30 |  | 1226771
Solano | Rio Vista | VAR170002 | 7008 | H9-04-026 | HSIP 9 | HSIP | HSIPL | 5099 | 015 | HSIPL-5099(015) | CON | Rio Vista: H9-04-026 Pedestrian Crossings |  |  | RFA at CT-HQ | 2021-10-04 | 2021-05-31 | 2020-05-14 |  | 2022-06-30 | 204600 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 204600 | [5 empty] | 204600 | 204600 | 9/16 - City will obligate funds in FFY20/21 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 204600
Solano | Solano County | SOL090015 | 4582 | RIP-T5-20-FED-SOL | RTIP | RTIP-FED |  | 5923 |  | -5923() | CON | Redwood-Fairgrounds Dr Interchange Imps | [7 empty] | 2022-06-30 | 5000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 5000000 |  |  | 5000000 | 5000000 | [5 empty] | 2021-09-30 |  | 5000000
Solano | STA | SOL110006 | 4313 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | RPSTPL | 5094 | 069 | RPSTPL-5094(069) | CON | Jepson: Leisure Town Road Phase 1B and 1C |  |  |  |  | 2022-06-01 | 2019-04-29 | 2022-01-31 | 2022-01-31 | 1407000 |  |  | 0 | [6 empty] | 0 |  |  | 1407000 | 1407000 | [6 empty] | 1407000 | 1407000 | 9/7/21 - Funds are moved out to FFY23. |  |  |  |  | 2021-09-30 |  | 1407000
Solano | STA |  |  | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6249 |  | -6249() |  | Solano Integration and Coordination Implementation Planning | [7 empty] | 2022-09-30 | 500000 |  |  | 0 | [6 empty] | 0 |  | 500000 |  | 500000 | [6 empty] | 500000 | 500000 | 8/30/21 - STA will add the project to the TIP in November and obligate. |  |  |  |  | 2021-09-30 |  | 500000
Solano | STA | SOL110006 | 4313 | EARMARK-T5-RE | EARMARK | EARMARK |  | 6249 |  | -6249() | CON | Jepson: Leisure Town Road Phase 1B and 1C | [7 empty] | 2022-01-31 | 81047 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 81047 | 81047 | 81047 | [5 empty] | 2021-09-30 |  | 81047
Solano | STA | SOL150003 | 6271 | RIP-T5-18-FED-SOL | RTIP | RTIP-FED |  | 6249 |  | -6249() | CON | SR12/Church Rd Intersection Improvements | [7 empty] | 2022-06-30 | 1939000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 1939000 |  |  |  | 1939000 | 1939000 | [5 empty] | 2021-09-30 |  | 1939000
Solano | Vacaville | VAR170002 | 6986 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5094 | 071 | HSIPL-5094(071) | CON | H9-04-035 Vacaville Signal Improvements |  |  |  |  | 2022-02-08 | 2019-07-16 | 2021-12-31 | 2022-06-30 | 2027700 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 2027700 | [5 empty] | 2027700 | 2027700 | 6/25 - Project confirmed by Tracy |  |  |  |  | 2021-09-30 |  | 2027700
Solano | Vacaville | SOL110006 | 4313 | RIP-T4-12-FED-SOL | RTIP | RTIP-FED | RSTPLR | 5094 | 069 | RSTPLR-5094(069) | CON | Jepson: Leisure Town Road Phase 1B and 1C |  | Jan/Feb 2022 |  |  | 2022-04-12 | 2019-04-29 | 2022-01-14 | 2022-06-30 | 3296000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 3296000 |  |  |  | 3296000 | 3296000 | 6/25 - Project confirmed by Tracy |  |  |  |  | 2021-09-30 |  | 3296000
Solano | Vacaville | SOL110006 | 4313 | RIP-T5-18-FED-SOL | RTIP | RTIP-FED | RSTPLR | 5094 | 069 | RSTPLR-5094(069) | CON | Jepson: Leisure Town Road Phase 1B and 1C |  | Jan/Feb 2022 |  |  | 2022-04-12 | 2019-04-29 | 2022-01-14 | 2022-06-30 | 6000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 6000000 |  |  |  | 6000000 | 6000000 | 6/25 - Project confirmed by Tracy |  |  |  |  | 2021-09-30 |  | 6000000
Solano | Vallejo | SOL190004 | 6916 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5030 | 067 | STPL-5030(067) | CON | Vallejo - Sacramento St Road Diet and Rehab |  |  |  |  | 2022-01-31 | 2020-06-09 | 2021-10-01 | 2022-01-31 | 681000 |  |  | 0 | [6 empty] | 0 |  | 681000 |  | 681000 | [6 empty] | 681000 | 681000 | [5 empty] | 2021-09-30 |  | 681000
Solano | Vallejo | SOL150004 | 6270 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5030 |  | -5030() | CON | STA SR2S Infrastructure & Non-infrastructure | [7 empty] | 2022-09-30 | 600000 |  |  | 0 | [6 empty] | 0 |  | 600000 |  | 600000 | [6 empty] | 600000 | 600000 | [5 empty] | 2021-09-30 |  | 600000
Solano | Vallejo | SOL170008 | 6558 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5030 |  | -5030() | CON | Vallejo Bay Trail / Vine Trail Gap Closure |  |  |  |  | 2022-04-01 |  |  | 2022-09-30 | 1800000 |  |  | 0 | [6 empty] | 0 |  | 1800000 |  | 1800000 | [6 empty] | 1800000 | 1800000 | [5 empty] | 2021-09-30 |  | 1800000
Solano | Vallejo | VAR170002 | 7004 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5030 | 065 | HSIPL-5030(065) | CON | H9-04-037 Vallejo: HSIP 6 HAWK Installation | [7 empty] | 2022-06-30 | 1155800 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1155800 | [5 empty] | 1155800 | 1155800 | [5 empty] | 2021-09-30 |  | 1155800
Solano | Vallejo | VAR170002 | 7003 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5030 | 066 | HSIPL-5030(066) | CON | H9-04-038 Vallejo HSIP 5 Pedestrian Crossings | [7 empty] | 2022-06-30 | 221000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 221000 | [5 empty] | 221000 | 221000 | [5 empty] | 2021-09-30 |  | 221000
Sonoma | Cotati | SON210002 | 7226 | STP-CRRSAA | OBAG2 | CRRSAA+ |  | 5383 |  | -5383() | CON | Cotati Downtown-Civic Center Connectivity Safety | [5 empty] | 2021-10-12 |  | 2022-09-30 | 2016000 |  |  | 0 | [6 empty] | 0 |  | 1008000 |  | 1008000 | [5 empty] | 1008000 | 2016000 | 2016000 | 8/23 - City confirmed project for FFY21/22, possibly early 2022. Need to follow up with FR |  |  |  |  | 2021-09-30 |  | 2016000
Sonoma | Cotati | SON210002 | 7226 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5383 |  | -5383() | CON | Cotati Downtown-Civic Center Connectivity Safety | [5 empty] | 2021-12-21 |  | 2022-09-30 | 242000 |  |  | 0 | [6 empty] | 0 |  | 242000 |  | 242000 | [6 empty] | 242000 | 242000 | 8/23 - City confirmed project for FFY21/22, possibly early 2022. Need to follow up with FR |  |  |  |  | 2021-09-30 |  | 242000
Sonoma | Healdsburg | SON170024 | 6623 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5027 |  | -5027() | CON | Healdsburg Avenue Complete Streets Improvements | [7 empty] | 2022-01-31 | 600000 |  |  | 0 | [6 empty] | 0 |  | 600000 |  | 600000 | [6 empty] | 600000 | 600000 | 8/24/21 - Will remove project from AOP. This project is waiting for ATP final approval in October. I have been in communication with both Karl Anderson and Mallory Atkinson. It is assumed that we will receive ATP funds, in which case we will move the $600k to PE phase of work and use ATP for CON. But until I get approval regarding the ATP I am on hold. |  |  |  |  | 2021-09-30 |  | 600000
Sonoma | Healdsburg | SON210003 | 7237 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5027 |  | -5027() | OTHER | Healdsburg Electric Bike Share | [7 empty] | 2022-09-30 | 250000 |  |  | 0 | [6 empty] | 0 |  | 250000 |  | 250000 | [6 empty] | 250000 | 250000 | 8/25 - On schedule to meet Nov 1 deadline, They have requested FR but have not heard back from Caltrans. They will follow up again next week. |  |  |  |  | 2021-09-30 |  | 250000
Sonoma | Rohnert Park | SON210004 | 7249 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 5379 | 025 | STPL-5379(025) | CON | Rohnert Park Pedestrian Safety Improvements | [5 empty] | 2021-09-28 | 2021-11-01 | 2022-09-30 | 522000 |  |  | 0 | [6 empty] | 0 |  | 522000 |  | 522000 | [6 empty] | 522000 | 522000 | 8/25 - They just scheduled our Field Review for 9/28/21. We expect to get our RFA for Construction out by 11/1/21. |  |  |  |  | 2021-09-30 |  | 522000
Sonoma | Santa Rosa | SON210001 | 7221 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5028 |  | -5028() | PE | Santa Rosa Transit Mall Roadbed Rehabilitation | [7 empty] | 2022-09-30 | 144705 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 144705 | 144705 | 144705 | [5 empty] | 2021-09-30 |  | 144705
Sonoma | Santa Rosa | SON210001 | 7221 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 5028 |  | -5028() | CON | Santa Rosa Transit Mall Roadbed Rehabilitation | [7 empty] | 2022-09-30 | 723295 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 723295 | 723295 | 723295 | [5 empty] | 2021-09-30 |  | 723295
Sonoma | Santa Rosa | SON170023 | 6612 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5028 | 085 | STPL-5028(085) | CON | Santa Rosa Pavement Rehab of Various Streets |  |  |  |  | 2022-05-01 | 2021-06-22 | 2021-11-01 | 2022-01-31 | 1655000 |  |  | 0 | [6 empty] | 0 |  | 1655000 |  | 1655000 | [6 empty] | 1655000 | 1655000 | [5 empty] | 2021-09-30 |  | 1655000
Sonoma | Santa Rosa | SON190011 | 7163 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5028 | 084 | STPL-5028(084) | CON | SantaRosa Downtown Comm Infrastructure Enhancement |  |  |  |  | 2022-05-01 | 2020-11-30 | 2021-11-01 | 2022-01-31 | 400000 |  |  | 0 | [6 empty] | 0 |  | 400000 |  | 400000 | [6 empty] | 400000 | 400000 | [5 empty] | 2021-09-30 |  | 400000
Sonoma | SCTA |  |  | STP-T5-OBAG2-REG-SSM | OBAG2 | STP |  | 6364 |  | -6364() |  | Sonoma Integration and Coordination Implementation Planning | [7 empty] | 2022-09-30 | 750000 |  |  | 0 | [6 empty] | 0 |  | 750000 |  | 750000 | [6 empty] | 750000 | 750000 | [5 empty] | 2021-09-30 |  | 750000
Sonoma | Sebastopol |  |  | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5123 |  | -5123() |  | Sebastopol SR 116 and Bodega Ave Pedestrian Access and Mobility Enhancements | [7 empty] | 2022-09-30 | 476000 |  |  | 0 | [6 empty] | 0 |  | 476000 |  | 476000 | [6 empty] | 476000 | 476000 | [5 empty] | 2021-09-30 |  | 476000
Sonoma | SMART |  | 7294 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  |  |  | -() | CON | SMART Rail and Pathway (Phase 2) | [7 empty] | 2022-09-30 | 806000 |  |  | 0 | [6 empty] | 0 |  | 806000 |  | 806000 | [6 empty] | 806000 | 806000 | [5 empty] | 2021-09-30 |  | 806000
[21 empty] | 334371501.0221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92802159 | 16406893 | 109209052 | 33143150 | 55706180.4821 | 72694490 | 27402000 | 0 | 36216628.54 | 334371501.0221 | 334371501.0221 | [7 empty] | 334371501.0221
J:\PROJECT\Funding\T5-FAST\STP-CMAQ\Obligations and Delivery\Annual Obligation Plans\FY 2021-22\[MTC FFY21-22 Annual Obligation Plan.xlsx]FFY 2021-22 Sep 30 |  | J:\170005 |  |  | 176 | [27 empty] | 13371820 | 56215288 | 69587108
Brought over from FFY20/21 | [23 empty] | 106856993
Remove from FFY21/22 AOP | [20 empty] | 2006820 |  | #REF! | 106856993
Confirmed for FFY21/22 | [22 empty] | 25000000 | [19 empty] | 12/13 - SJ needs to work with MTC on TIP Revision
Sponsor has requested to remove and/or not responded and will remove upon final submission to CT | [19 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
Wants to move out, but needs to address Inactive Obligations for TIP programming change. | [22 empty] | 0
Follow up for FR, Award date, SPOC, HPMS, or more info by 9/23 | [22 empty] | #REF!
Extension CTC extension request/approval | [20 empty] | #REF! |  | #REF!
Missed delivery in FFY20/21
S&S Mobility QS not in FMS
Need HPMS reporting | Need HPMS reporting | [21 empty] | #REF!
Allocated but needs obligation
#REF!
123556965
[21 empty] | #REF! | #REF! | #REF! | #REF!
#REF!
Note on N14: John Saelee: May '20: $2.445M of STIP allocated to AlamedaCTC for ROW, State-Only. Caltrans is implementing the Con phase. August '20: $16.816M STIP (and $4.152M ATP) allocated to Caltrans for Phase 1 (2323A) Con, starting 12/2020. Phase 2 (2323B) allocation of $19.523M balance is Est. Dec 2020 w/ Con start: 4/2021.
Note on D36: John Saelee: Allocation dead;ine extendd to 8/31/22
Note on F37: John Saelee: Need to Coordinate RFA with ATP allocation June 22. Funds programmed in FFY23 in TIP - move up in TIP or use EPSP?
Note on D41: John Saelee: CCTA will work with MTC staff to see if the Study can be funded through FTA and therefore not have to go to DLAE. FTA transfer will be completed before 9/30/22.
Note on T58: John Saelee: The Pavement Project already had the Field Review and was nearing getting NEPA clearance. With the addition of Cycle Track, they have to do a quick revision. They have already spoken to CT DLAE.
Note on T59: John Saelee: The Pavement Project already had the Field Review and was nearing getting NEPA clearance. With the addition of Cycle Track, they have to do a quick revision. They have already spoken to CT DLAE.
Note on W61: John Saelee: 9/16/21 - Obligated $506,812.49 on MRN970016. Balance of $887,051.51 will be reprogrammed to MRN050018 in Nov/Dec TIP Revision.
Note on D75: John Saelee: Allocated but needs oblgiation?
Note on D99: John Saelee: Allocated but needs oblgiation?
Note on D130: John Saelee: Allocated but needs oblgiation? State Only Funds?
Note on D131: John Saelee: Will allocate FFY21-22. State Only Funds?
Note on D145: John Saelee: State Only Funds?
Note on D150: John Saelee: Does this need an obligation?